Annex: Fully Costed Evaluation Plan – Jordan (2023-2027)\*

|  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **UNDAF/****CPD Outcome** | **Strategic Plan Outcome** | **Evaluation Title** | **Partners (joint evaluation)** | **Evaluation commissioned by (if not****UNDP)** | **Type of evaluation** | **Planned Evaluation CompletionDate** | **Estimated Cost In USD** | **Provisional Source of Funding** |
| Enhanced inclusive, gender-responsive and green growth in Jordan that provides access to entrepreneurship and decent work opportunities, life-long learning, and market-relevant skills with a focus on LNOB  | No one left behind, centering on equitable access to opportunities and a rights-based approach to human agency and human development | Outcome Evaluation - Green Economic Growth for Jordan (Private Sector Engagement, Livelihoods and SDG Accelerator) | N/A | N/A | Outcome | 2026Quarter 3 | 60,000 | Project/ M&E budget  |
| Mid Term Project Evaluation – Improving Local Development to Increase the Resilience of Host Communities and Refugees in North Jordan (Mid Term) | European Union (EU) | N/A | Project | 2025Quarter 1 | 40,000 | Project/ M&E budget |
| Final Project Evaluation – Improving Local Development to Increase the Resilience of Host Communities and Refugees in North Jordan  | EU | N/A | Project  | 2027 Quarter 3 | 60,000 | Project/ M&E budget |
| Final Project Evaluation – Livelihood opportunities through rehabilitation of public schools | King Salman Relief-Saudi Arabia | N/A | Project | 2024Quarter 2 | 15,000 | KSRelief |
| Final Project Evaluation - Social Entrepreneurship  | N/A |  N/A | Project | 2024Quarter 4 | 20,000 | Different Projects Budget |
| Final Project Evaluation - Women’s Economic Empowerment through SWM | Global Affairs Canada | N/A | Project | 2023Quarter 4 | 30,000 | Project/ M&E budget |
| Enhanced national resource management models that ensure equitable access to water, food, and clean energy for all, address climate related and other risks, and empower local communities as agents of change for responsible production and consumption | Resilience built to respond systemic uncertainty and risk | Final Project Evaluation - Sustainable Urbanization and Resource Efficiency | Greater Amman Municipality | N/A |  Project | 2026Quarter 4 | 25000 | GEF |
| Final Project Evaluation – MSB II Regional Programme | Birdlife International | N/A | Project | 2023Quarter 1 | 35,000 | GEF |
| Final Project Evaluation – Reduction and Elimination of Persistent Organic Pollutants | MOEnv | N/A | Project | 2025Quarter 4 | 25,000 | GEF |
|  Final Project Evaluation - Water Management / drought governance |  MWI, MoEnv | N/A |  Project | 2025Quarter 1 | 45000 | GCF  |
| Thematic Evaluation – Resilience - Afforestation, Protected and Marine Areas Management  | ASEZA, MoEnv | N/A | Thematic  |  2027Quarter 4 | 50,000 | C/S |
| Enhanced accountability and responsiveness of Jordanian institutions and their partners, and especially women and youth are increasingly and meaningfully involved in policy choices and decisions that affect their lives choices and decisions that affect their lives | Structural transformation accelerated, particularly green, inclusive, and digital transitions | Portfolio Evaluation - Holistic and Transformative Systems and Capacities (HTSC)  | MoDEE, MoPIC, MoI | N/A | Portfolio | 2026Quarter 4 | 60,000 | C/S |
| Final Project Evaluation - NLG (Network of Local Governments)  | MoLA | N/A | Project | 2023Quarter 1 | 30000 | Project/ M&E budget |
| Final Project Evaluation – Decentralization Accountability and Integrity at the Local Level (DAILL) | EU | N/A | Project | 2024Quarter 4 | 50,000 | EU |
| Thematic Evaluation – Digitalization - Bridging the Digital Divide  |  N/A | N/A  | Thematic/ Digitalization | 2027Quarter 2 | 30,000 | Different Projects Budget |
| Thematic Evaluation - Gender - Women’s Participation in Political Spheres (parliament/ IEC) |  N/A | N/A  | Thematic / Gender  |  2026Quarter1 | 40,000 | Project/ M&E budget |
| Final Project Evaluation - Development Services Agreement  | MoLA | N/A | Project | 2025Quarter 3 | 30,000 | Project/ M&E budget |
| ALL | ALL | CPD midterm review | UNDP, MOPICGovernment & IPs | N/A | Midterm | 2025Quarter 4 | 75,000 | C/S TRAC |

**The evaluation includes all mandatory project evaluations as specified in the UNDP Evaluation Guidelines, a total of 12 for the new programme cycle. The evaluation plan is focused on establishing an evidence base of knowledge, experience, success and learnings on results to inform and strengthen work within the country, the region, and the wider organization. The plan includes an outcome evaluation for the Green Growth outcome, as this is a relatively new area of work within the CF and the CPD, and therefore timely monitoring is critical for maximum success in achieving results. As the UNDP’s CPD 2023-27 is introducing a portfolio approach for the first time in Jordan and the region, a portfolio evaluation for the ‘Holistic and Transformative Systems and Capacities (HTSC)’ is included in the plan, to be conducted in the penultimate year of the Programme Cycle, to evaluate both results of the portfolio and the feasibly of the approach. Thematic evaluations have been planned to measure progress on digitalization, resilience and gender mainstreaming within the programme. An MTR for the Country Progamme has also been planned.**