Integrated UN Programme for Montenegro

PHASE II (2012 – 2016) – Draft Results Matrix

Introduction

This draft Results Matrix is the result of a process of intensive dialogue with government and internal consultations between UN agencies.  A two-day “Strategic Validation Retreat” was held in mid-October at which senior government officials and UN representatives and programme staff engaged in discussing national development priorities and the role of the UN system is supporting the achievement of them.  This Retreat also validated the Pillar structure and Outcomes of the Phase I (2010 – 2011) Integrated UN Programme.

General scenario and assumptions:

The Core Resources of resident UN agencies will be less in Phase II than in Phase I of the Integrated UN Programme.  Therefore, Non-core or Extra-budgetary Resources and strategic partnerships with other development actors will be vital to a successful Phase II.  Overall, however, there will be a scaling-down of UN system cooperation from 2015 onwards, although this would need to be confirmed at the Mid-term Review of Phase II in late 2014.

There will be a growing partnership of UN, World Bank and EU in all Pillars.  In order for EU accession negotiations to commence (2013), the political criteria need to be met and the benchmarks in social inclusion and democratic governance must be reached as quickly as possible.  IPA resources channeled through the UN are reflected in 30 month periods spanning 2011, 2012 and 2013 (IPA 2010), 2012, 2013 and 2014 (IPA 2011) and so on for IPA 2012 and IPA 2013.  While candidate status (2010) will give access to IPA III and IV components, the total value of IPA support will be unchanged until 2014 when a new Strategic Coherence Framework (Financial Perspective) will take effect.

There will be continued access to, but growing dependency on, global funds and agency-specific “vertical” funds for cooperation in all Pillars.  The scale-down of programme activity will be slowest in the SEDEP Pillar, reflecting the long-term nature of the challenges, including climate change adaptation and balanced regional growth.

SOCIAL INCLUSION

Vision Statement and Strategic Development Goal:

Vision: a Montenegrin society that is progressively free of social exclusion and enjoys a quality of life that allows all individuals and communities to reach their full potential.  Further progress towards this vision will be achieved through focused investment in and resource allocations aimed at better housing, healthcare, education, social protection and employment, as well as greater opportunities for civic engagement, thus ensuring genuine participation of all members of society in economic, social, political and cultural life and achievement of adequate standards of living and wellbeing.

STRATEGIC DEVELOPMENT GOAL 1 – Montenegro’s society is progressively free of social exclusion and enjoys a quality of life that allows all individuals and communities to develop to their full potential.

Summary of UN system expenditure and Phase I budgetary framework:

| Participating UN organization: | UN System Expenditure: | Phase I Planned Budget: |
| --- | --- | --- |
|  | 2008 | 2009 | 2010 (estimate) | 2010 | 2011 |
| UNDP: | 1,798,482 | 1,715,912 | 2,196,147 | 2,396,147 | 2,305,969 |
| UNHCR: | 1,020,860 | 1,244,573 | 1,139,741 | 4,223,285 | 4,417,224 |
| UNICEF: | 582,590 | 1,046,836 | 2,591,050 | 4,210,750 | 1,556,839 |
| WHO: | 0 | 146,447 | 282,500 | 1,022,145 | 867,145 |
| IOM: | 810,049 | 283,662 | 367,865 | 367,865 | 0 |
| UN TGs / UNCT: | 60,692 | 72,200 | 45,030 | 45,030 | 0 |
| Total | 4,272,673 | 4,509,630 | 6,622,333 | 12,265,222 | 9,147,177 |

| Programme Outcome: | UN System Expenditure: | Phase I Planned Budget: |
| --- | --- | --- |
|  | 2008 | 2009 | 2010 (estimate) | 2010 | 2011 |
| Outside Phase I b/fwk | 1,579,966 | 737,949 | 8,000 | 8,000 | 0 |
| Outcome 1.1 | 0 | 45,498 | 639,100 | 1,272,200 | 355,295 |
| Outcome 1.2 | 332,900 | 658,437 | 2,055,792 | 3,364,807 | 1,541,887 |
| Outcome 1.3 | 2,359,807 | 3,067,746 | 3,919,441 | 7,620,215 | 7,249,995 |
| Total for SI Pillar | 4,272,673 | 4,509,630 | 6,622,333 | 12,265,222 | 9,147,177 |

Draft Phase II indicative budgetary framework:

| Programme Outcome: | Phase II Planned Budget, by year: | TOTAL 2012 - 2016 |
| --- | --- | --- |
|  | 2012 | 2013 | 2014 | 2015 | 2016 |  |
| Outside Phase II b/fwk | 0 | 0 | 0 | 0 | 0 | 0 |
| Outcome 1.1 | 500,000 | 500,000 | 300,000 | 200,000 | 100,000 | 1,600,000 |
| Outcome 1.2 | 1,000,000 | 1,000,000 | 700,000 | 500,000 | 300,000 | 3,500,000 |
| Outcome 1.3 | 2,500,000 | 2,500,000 | 1,000,000 | 500,000 | 200,000 | 6,700,000 |
| Total for SI Pillar | 4,000,000 | 4,000,000 | 2,000,000 | 1,200,000 | 600,000 | 11,800,000 |

Phase II Results framework:

| Pillar Outcome 1.1: | Montenegro’s legal framework is harmonized with EU/UN standards, and policies relevant to social inclusion are implemented and monitored |
| --- | --- |
| Indicators & sources of verification: % of relevant legislation and policies harmonized and implemented in line with UN and EU standards # of concluding observations by UN Committees fulfilled by the country |
| National development priority Focus Area agreed with the government | Participating UN Agencies | Indicative budget (US$) 2012-16, by agency | Key partners |
|  |  | Core | non-Core | Gap |  |
| Early Childhood Development Policy development of policy | UNICEF |  |  |  | MOES, MLSW, MOH, Council on the Rights of the Child |
|  | WHO |  |  |  |  |
| Public Health Strategy development of strategy | WHO |  |  |  | MOH, IPH |
|  | UNICEF |  |  |  |  |
| Child Care System Reform – law on child and social protection - fostering strategy | UNICEF |  | IPA 2010 Amount? |  | MLSW |
| Family Violence development of National Strategy support in implementing school curricula/training of teachers | UNDP | 20,000 |  |  | MLSW, MoJ, MMHR, MOI, MOES |
|  | UNICEF |  | IPA 2010 Amount? |  |  |
|  | WHO |  |  |  |  |
|  | IOM |  |  |  |  |
|  | UNHCR |  |  |  |  |
| Youth development of new Youth strategy development of Law on Youth and Sport | UNDP |  |  |  | MOES (Directorate of Sport and Youth) |
|  | UNICEF |  |  |  |  |
|  | IOM |  |  |  |  |
| Data, Monitoring and Evaluation Implementation of Laws, Policies (Anti-discrimination, asylum, foreigners, HIV/AIDS, mental health, disability etc) Implementation of recommendations from UN Committees Data and analysis – NHDR; DevInfo; | Which agency? | 150,000 |  |  | Relevant line ministries; Ombudsman; MONSTAT |
|  | All UN agencies |  |  |  |  |

| Pillar Outcome 1.2: | Social norms are embedded in order to facilitate age and gender sensitive inclusive attitudes and practices towards vulnerable and excluded populations |
| --- | --- |
| Indicators & sources of verification: The implementing mechanisms for preventing, monitoring, sanctioning and prosecuting discrimination are able to effectively address cases of discrimination (Sources of verification: EU progress reports, Ombusdman’s Reports, court records) % of population at risk with access to standardized preventive and protective services % of children and women provided with legal and social protection assistance to prevent and respond to violence |
| National development priority / Focus Area agreed with the government | Participating UN Agencies | Indicative budget (US$) 2012-16, by agency | Key Partners |
|  |  | Core | non-Core | Gap |  |
| Non communicable diseases mitigating risk factors and promoting healthy lifestyles mental health | WHO |  |  |  | MoH |
|  | UNICEF |  |  |  |  |
|  | UNDP |  |  |  |  |
| Food and Water Safety | WHO |  |  |  | MoH |
| Anti-discrimination | UNHCR |  |  |  | MMHR |
|  | IOM |  |  |  |  |
|  | UNICEF |  |  |  |  |
|  | UNDP |  |  |  |  |
| Domestic and sexual violence prevention of domestic violence and violence against women and children (attitudes and practices) norms and standards (violence) Preventive work around sexual and gender-based violence response commercial sexual exploitation of vulnerable groups, including children | UNHCR |  |  |  | MMHR, MLSW, MoJ, MOI, MOES, Office for Anti-Trafficking |
|  | IOM |  |  |  |  |
|  | UNICEF |  |  |  |  |
| Traffic safety | UNECE |  |  |  | MOT, MOI,MOJ, OSCE |
|  | WHO |  |  |  |  |
|  | UNICEF |  |  |  |  |
|  | UNDP |  |  |  |  |
| Child care system reform and Inclusion of Children with Disabilities standards awareness raising inclusion of children with disabilities | UNICEF |  | IPA 2010 Amount? |  | MLSW, MOES, MOH |
| Roma inclusion attitudes and practices | UNHCR |  |  |  | MMHR |
|  | UNDP |  |  |  |  |
|  | UNICEF |  |  |  |  |
|  | IOM |  |  |  |  |
| Gender mainstreaming | IOM |  |  |  | MMHR |
|  | UNDP |  |  |  |  |
|  | UNICEF |  |  |  |  |
|  | UNHCR |  |  |  |  |
| Health System Strengthening | WHO |  |  |  | MOH |
|  | UNDP |  |  |  |  |
| Communication for Development around social inclusion | UNICEF |  |  |  | GOM |
|  | UNHCR |  |  |  |  |

| Pillar Outcome 1.3: | Montenegro reduces disparities and gaps in access to quality health, education and social services, in line with EU/UN standards |
| --- | --- |
| Indicators & Sources of verification: # of new/innovative services established and implemented at local level through SIF % decrease in unemployment rate of hard-to-employ people (people with disabilities, single parents, long term unemployed, refugees/foreigners ) % of socially excluded children accessing early childhood and formal education % of refugees/foreigners accessing social/health rights through the national systems % of Konik area inhabitants who gain durable solutions |
| National development priority Focus Area agreed with the government | Participating UN Agencies | Indicative budget (US$) 2012-16, by agency | Key partners |
|  |  | Core | non-Core | Gap |  |
| Support to durable solutions for refugees/IDPs Humanitarian, legal and medical assistance Voluntary return | UNHCR |  |  |  | MLSW, BCR, MOI |
|  | IOM |  |  |  |  |
| Support to durable solutions for Konik | UNHCR |  |  |  | MLSW, BCR, Capital City Podgorica, MOE, MOI |
|  | UNDP |  |  |  |  |
|  | UNICEF |  |  |  |  |
| Roma inclusion education, health, social protection services including for children and Most At Risk Adolescents | UNHCR |  |  |  | MLSW, MOH, MOE |
|  | UNICEF |  |  |  |  |
|  | UNDP |  |  |  |  |
|  | IOM |  |  |  |  |
| Children and Persons with disabilities education, health and social protection services | UNICEF |  |  |  | MLSW, MOE, MOH, municipalities |
|  | UNDP |  |  |  |  |
|  | UNHCR |  |  |  |  |
| Mental Health implementation of action plan | WHO |  |  |  | MOH, MLSW |
|  | UNDP |  |  |  |  |
|  | UNICEF |  |  |  |  |
| Containment of communicable diseases | WHO |  |  |  | MOH |
|  | UNICEF |  |  |  |  |
| Social welfare system reform SIF and SIP (IPA 2010) (De-institutionalization of services for children and adults) | UNDP | 160,000 | 1,600,000 |  | MLSW, municipalities |
|  | UNICEF |  |  |  |  |
| HIV/AIDS and Tuberculosis Prevention (refugee youth; MARA; migrant workers) HIV/AIDS Strategy implementation Tuberculosis control | UNDP (GFATM Round 6 TB and Round 9 HIV/AIDS) |  | 800,000 |  | MOH, IPH, CCM |
|  | UNICEF |  |  |  |  |
|  | UNHCR |  |  |  |  |
|  | WHO |  |  |  |  |
|  | IOM |  |  |  |  |
|  | UNAIDS (PAF) |  | 300,000 |  |  |
| Young People’s Health, Development and Protection | UNDP |  | 400,000 |  | MOH, MLSW |
|  | UNICEF |  |  |  |  |
|  | IOM |  |  |  |  |
|  | WHO |  |  |  |  |
| Work with long term unemployed (linked to increased mobility programme) | UNDP |  |  | 2,000,000 | MLSW, Bureau for Employment |
| Emergency Preparedness and Response | All UN agencies |  |  |  | MOI, GOM |

DEMOCRATIC GOVERNANCE

Vision Statement and Strategic Development Goal:

Vision: a Montenegro that is a democratic society, that fully respects, protects and fulfils human rights through rule of law, government transparency and accountability.  A Montenegro that is able to meet the political criteria for EU accession and is ready to assume EU membership obligations.

STRATEGIC DEVELOPMENT GOAL 2 – Fostering a democratic society that fully respects, protects and fulfils human rights through rule of law, government transparency and accountability.

Summary of UN system expenditure and Phase I budgetary framework:

| Participating UN organization: | UN System Expenditure: | Phase I Planned Budget: |
| --- | --- | --- |
|  | 2008 | 2009 | 2010 (estimate) | 2010 | 2011 |
| UNDP: | 1,916,418 | 1,999,734 | 3,683,000 | 8,354,723 | 7,420,490 |
| UNHCR: | 466,915 | 657,344 | 918,617 | 1,057,569 | 1,034,307 |
| UNICEF: | 238,263 | 713,838 | 927,620 | 1,215,020 | 189,300 |
| WHO: | 0 | 0 | 0 | 0 | 0 |
| IOM: | 3,130 | 124,654 | 637,793 | 1,296,636 | 521,657 |
| UN TGs / UNCT: | 24,900 | 51,469 | 18,000 | 18,000 | 0 |
| UNESCO: | 0 | 0 | 50,000 | 95,000 | 0 |
| Total | 2,649,626 | 3,547,039 | 6,235,030 | 12,036,948 | 9,165,754 |

| Programme Outcome: | UN System Expenditure: | Phase I Planned Budget: |
| --- | --- | --- |
|  | 2008 | 2009 | 2010 (estimate) | 2010 | 2011 |
| Outside Phase I b/fwk | 843,994 | 515,320 | 7,000 | 104,843 | 0 |
| Outcome 2.1 | 22,117 | 282,493 | 315,970 | 414,770 | 120,000 |
| Outcome 2.2 | 1,050,307 | 1,969,361 | 7,297,373 | 10,186,166 | 7,739,257 |
| Outcome 2.3 | 491,815 | 779,865 | 1,141,417 | 1,331,169 | 1,306,497 |
| Total for DG Pillar | 2,408,233 | 3,547,039 | 8,761,760 | 12,036,948 | 9,165,754 |

Draft Phase II indicative budgetary framework:

| Programme Outcome: | Phase II Planned Budget, by year: | TOTAL 2012 - 2016 |
| --- | --- | --- |
|  | 2012 | 2013 | 2014 | 2015 | 2016 |  |
| Outside Phase II b/fwk | 0 | 0 | 0 | 0 | 0 | 0 |
| Outcome 2.1 | 300,000 | 200,000 | 100,000 | 0 | 0 | 500,000 |
| Outcome 2.2 | 4,000,000 | 3,000,000 | 2,000,000 | 1,000,000 | 500,000 | 10,500,000 |
| Outcome 2.3 | 1,000,000 | 1,000,000 | 500,000 | 500,000 | 500,000 | 3,500,000 |
| Total for SI Pillar | 5,300,000 | 4,200,000 | 2,600,000 | 1,500,000 | 1,000,000 | 14,500,000 |

Phase II Results framework:

| Outcome 2.1: | National legislative framework is harmonized with UN, EU and CoE standards and relevant secondary legislation regulating implementation is developed. |
| --- | --- |
| Indicators & Sources of verification | Degree of harmonization of legal Framework (laws and bylaws) with UN Conventions, EU, CoE and National frameworks (partially compliant, fully, compliant, not compliant). Existence of law on legal Aid and relevant bylaws (Baseline: does not exist; Target: Law and bylaws exist) law on Juvenile Justice; (Baseline: does not exist; Target: Law and bylaws exist) Sources: EU progress reports; EU Sectoral screening/ aquis; Ministerial Legal assessments (% target), CoE compliance reports; UN convention reporting (CEDAW, CRC) |
| Focus Area | UN Agency(ies) with mandate | Indicative budget (US$) 2012-16 Core / non-Core | Key partners |
| 1.1 Child Rights, Policy and Planning | 1.1.1 Justice for children: -Relevant legislation; - Juvenile justice system reform; -Protecting children against violence, torture, trafficking and any other form of exploitation. | UNICEF |  | Ministry of Justice |
| 1.2 Rule and law and Human Rights | 1.2.1 Implementation of: -Juvenile justice law -Law on protection against family violence ; | UNICEF |  | Ministry of Justice |
|  | 1.2.2. Centre for Mediation and Alternative Sanctions | UNDP/UNICEF | 90,000 | Ministry of Justice |
|  | Reform of Legal Aid System | UNDP/UNICEF |  | Ministry of Justice |
| 1.3 Harmonization of national legal framework | Harmonization with amended law on foreigners Amending of the Law of Asylum Harmonization with UN Conventions on Statelessness | UNHCR |  | Ministry of Interior |
| Strengthening Science, technology and Innovation Governance and Assessment : Review the National STI and Higher Education strategies and support the national authorities in the implementation and monitoring of the action plans with special focus on youth and gender | UNESCO |  |  |

| Outcome 2.2: | State and Independent Institutions with increased capacity to ensure the realization and monitoring of human rights, support empowerment of women, enable equal opportunities for all inhabitants, including access to efficient service delivery through a transparent system of public administration at national and local level |
| --- | --- |
| Indicators & Sources of verification | Transparency International Index (2010:3.7); Rate and pace of success in meeting EU progressive benchmarks (2010: candidacy status; 7 specific benchmarks set) Number of UNHCR persons of concern with access to documentation (Source: UNHCR) % of foreigners with access to rights and services (source: UNHCR) Percentage of complaints to Ombudsman addressed and resolved (disaggreagated: men/women/children) (Baseline X; Target X) Number cases accessing legal aid (disaggregated: men/women/children); Number of cases using mediation (Baseline: data collection on legal aid provision & mediation cases to begin end 2011. Target: 200 cases of legal aid per year; 15% of cases going through mediation) Improvements in perception of quality of state services, (Survey:”Transparency of the State Administration”) (Baseline: rating 6/10 on Quality (2010) Target: rating 7/10 by 2014.) |
| Focus Area | UN Agency(ies) with mandate | Indicative budget (US$) 2012-16 Core / non-Core | Key partners |
| 2.1 Public Administration Reform (central level) EC benchmark # 2, 3, 4 & 5 | 2.1.1. Child Rights, Policies and Planning Human resource development; Establishment of sustainable infrastructure for data collection, priority settings, policy planning and monitoring; Deinstitutionalization; Decentralization of services; Gender equality; | UNICEF |  |  |
|  | 2.1.2 Capacity Development Programme (CD Programmes for Ministry of Foreign Affairs, Ministry of Finance, Ministry of European Integration Deputy Prime Minister cabinets on PAR and donor coordination) | UNDP |  | Ministry of Foreign Affairs |
|  | 2.1.3 Strengthening capacities of the Directorate for Anti Corruption | UNDP | $80,000 | DACI |
|  | 2.1.4 Governance in the Health Sector | WHO, UNDP |  | Ministry of Health |
|  | 2.1.5 Capacity Strengthening of Ministry of Justice | UNDP |  | Ministry of Justice |
|  | 2.1.6 Strengthening capacities in the judiciary to fight corruption and organized crime | UNDP |  | Ministry of Justice |
|  | 2.1.7 Strengthening capacities of service delivery institutions and complaint mechanisms in the area of employment, and of security sector actors, on gender equality | UNIFEM | Non-core – $ 85,000 (for 2012) For 2013-16 - TBD |  |
| 2.2 Public Administration Reform (local level) | 2.2.1 Local Governance (Organizational development and municipal networking focusing on inter-municipal cooperation) | UNDP |  | Ministry of Interior |
|  | 2.2.2 Decentralization of Services for Children | UNICEF |  |  |
|  | 2.2.3 Strengthening mechanisms for public finance at the local level | UNDP | $535,045 (2012 – Netherlands) | Ministry of Interior |
| 2.3 Asylum and statelessness | 2.3.1 Strengthening Capacities of the Asylum System | UNHCR |  | Ministry of Interior |
|  | 2.3.2 Strengthening Capacities in the area of statelessness and prevention of statelessness | UNHCR |  | Ministry of Interior |
| 2.4 Euro-Atlantic Integration | 2.4.1 Storage upgrade and Demilitarization Programme: Small Arms and Light Weapons | UNDP |  | Ministry of Defense |
| 2.5 Migration | 2.5.1 Support to Migration Management in Montenegro | IOM |  | Police? |
|  | 2.5.2 Capacity strengthening in support of Montenegro’s Migration information System | IOM |  |  |

| Outcome 3: | Empower Civil Society and supportive institutional mechanisms to increase awareness on human rights and the benefits and obligations of participation in decision making, advocacy, demanding quality services and accountability |
| --- | --- |
| Indicators & Sources of verification | Number of NGOs participating in reporting on UN Conventions or Shadow Reports (Source: Annual Report of office for cooperation with Civil Society) Sustainability of NGO funding (source: USAID NGO Sustainability Index) Percentage of women elected officials at national and local levels (Baseline: 11% in parliament; 1 (in 17) Minister; 1 (in 21) Mayor. Target: 30% at all levels Number of municipalities with Children’s Parliaments (baseline X; Target X); |
| Focus Area | UN Agency(ies) with mandate | Indicative budget (US$) 2012-16 Core / non-Core | Key Partners |
| 3.1 Child Protection | 3.1.1. Strengthening of children’s capacity to participate in all matters that concern them; 3.1.2. Activating and scaling up the model of child participation in schools, municipalities and relevant initiatives at national level; 3.1.3. Empowerment of Child Rights related civil sector organization; | UNICEF |  |  |
|  | 3.1.4. Capacity building of Ombudspersons’ Office (Department for Child Rights) in CR promotion, protection and monitoring; 3.1.5. Empowerment of children to approach Ombudsperson`s Office and supporting the Office in development of preconditions re: accessibility for all children to file complaints on CR violations. | UNICEF |  |  |
| 3.2 Gender equality | 3.3.1 Women’s Political Empowerment; Women’s Economic Empowerment | UNDP | $646,372 (2012 & 2013 IPA) | Department for gender Equality/Ministry of Minorities and human Rights. |
|  | 3.3.2 Strengthening capacities of gender equality mechanisms at national and local levels and of civil society organizations to uphold women’s economic rights | UNIFEM | Non-core – $ 50,000 (for 2012) For 2013-16 - TBD |  |

SUSTAINABLE ECONOMIC DEVELOPMENT & ENVIRONMENTAL PROTECTION (SEDEP)

Vision Statement and Strategic Development Goal:

Vision: a Montenegrin society that translates its Constitutional commitment to the concept of an ‘ecological state’ into practice through achieving balanced and equitable regional economic growth based on sustainable planning and use of natural resources that will provide high quality of life and long term economic opportunities for its inhabitants.

STRATEGIC DEVELOPMENT GOAL 3 – Balanced and equitable regional economic growth based on sustainable planning and use of natural resources that will provide high quality of life and long term economic opportunities for its inhabitants.

Summary of UN system expenditure and Phase I budgetary framework:

| Participating UN organization: | UN System Expenditure: | Phase I Planned Budget: |
| --- | --- | --- |
|  | 2008 | 2009 | 2010 (estimate) | 2010 | 2011 |
| UNDP: | 2,006,816 | 2,477,018 | 2,490,000 | 8,330,294 | 4,370,763 |
| UNESCO: | 0 | 0 | 270,000 | 270,000 | 240,000 |
| UNEP: | 450,000 | 0 | 312,471 | 312,471 | 420,000 |
| UNIDO: | 164,286 | 208,207 | 181,024 | 181,024 | 262,500 |
| FAO: | 367,171 | 673,518 | 1,049,364 | 1,049,364 | 632,500 |
| UNICEF: | 0 | 0 | 25,000 | 25,000 | 25,000 |
| WHO: | 0 | 19,233 | 57,000 | 57,000 | 57,500 |
| Total | 2,988,273 | 3,377,976 | 4,384,859 | 10,225,153 | 6,008,263 |

| Programme Outcome: | UN System Expenditure: | Phase I Planned Budget: |
| --- | --- | --- |
|  | 2008 | 2009 | 2010 (estimate) | 2010 | 2011 |
| Outside Phase I b/fwk | 682,503 | 52,860 | 0 | 0 | 0 |
| Outcome 3.1 | 834,125 | 958,739 | 1,784,201 | 5,046,672 | 2,246,963 |
| Outcome 3.2 | 750,433 | 1,286,638 | 905,688 | 1,405,688 | 898,800 |
| Outcome 3.3 | 721,212 | 1,079,739 | 1,830,293 | 3,772,793 | 2,862,500 |
| Total for SEDEP Pillar | 2,988,273 | 3,377,976 | 4,520,182 | 10,225,153 | 6,008,263 |

Draft Phase II indicative budgetary framework:

| Programme Outcome: | Phase II Planned Budget, by year: | TOTAL 2012 - 2016 |
| --- | --- | --- |
|  | 2012 | 2013 | 2014 | 2015 | 2016 |  |
| Outside Phase II b/fwk | 0 | 0 | 0 | 0 | 0 | 0 |
| Outcome 3.1 | 2,500,000 | 2,500,000 | 2,000,000 | 1,000,000 | 1,000,000 | 9,000,000 |
| Outcome 3.2 | 1,000,000 | 1,000,000 | 750,000 | 500,000 | 0 | 3,250,000 |
| Outcome 3.3 | 1,500,000 | 1,000,000 | 1,000,000 | 750,000 | 500,000 | 4,750,000 |
| Total for SI Pillar | 5,000,000 | 4,500,000 | 3,750,000 | 2,250,000 | 1,500,000 | 17,000,000 |

| Outcome 3.1: | Climate change adaptation and mitigation measures are designed and implemented to accelerate the use of renewable, clean energy, carbon trading and energy efficiency, thereby achieving low carbon emissions, climate resilient growth and better management of human health impacts. |
| --- | --- |
| Indicators & sources of verification 1. Number of legislative, institutional and regulatory measures from the key strategic documents (NEDS, Energy Efficiency Strategy and Action Plan, Strategy for Formalization of Informal Settlements) harmonized with the EU and UN and implemented Sources: Annual/Biannual progress reports on strategies’ implementation, EU progress reports, UN reports |
| National development priority Focus Area agreed with the government | Participating UN Agencies | Indicative budget (US$) 2012-16, by agency | Key Partners |
|  |  | Core | non-Core | Gap |  |
| Low Carbon Dev. Strategy | UNDP: Strategic planning, NAMAs UNWTO: know-how and best practices on reduction of CO2 emissions from tourism. | UNDP | 11,500 |  | 400,000 | Ministry of Spatial Planning & Environment |
|  |  | UNWTO | 10,000 | 50,000 |  |  |
| Environmental Monitoring and Reporting | UNDP: environmental indicators incl. ‘2nd National Communication to the UNFCCC’ and ‘Capacity Building for integration of global environment commitments in investment and development decisions’ | UNDP | 50,000 40,000 | 60,000 | 500,000 | Ministry of Spatial Planning & Environment |
|  |  | UNECE | 40,000 |  |  |  |
|  | UNDP: Capacity building - reporting UNECE – environmental indicators | UNDP | 20,000 |  | 500,000 |  |
|  |  | UNECE |  |  |  |  |
| Energy efficiency (EE) | Industrial EE - Mandatory LIR framework from the acquis implemented in national legislation (Strategy EE 2005, EEAP 2010-2012) and promotion of EE measures financing in the industrial sector, especially in SMEs sector to reduce energy intensity and promote cleaner production | UNIDO |  | 200,000 |  | Ministry for Economic Development |
|  | Energy efficiency market formation - Investment climate created for increase in EE investments and infrastructural projects (EEAP 2010-2012, Strategy EE 2005) - Strong framework for removal of the barriers from private sector (Strategy EE, 2005 and EEAP 2010-2012) | UNECE | 50,000 | 100,000 |  |  |
|  | Residential EE - energy governance and financial infrastructure, energy performance standards and technology integration, and access to EE and public housing - - Mandatory LIR framework from acquis implemented in the national legislation, including adequate statistics and monitoring system (Strategy EE 2005, EEAP 2010-2012) - Institutional capacity strengthened to promote EE in residential sector (EE Strategy, 2005, EEAP 2010-2012) - Reduction of energy costs for households, increasing the living comfort, health and safety, and playing a significant role in the improvement of the situation of the poorest population (EE Strategy, 2005) - Sustainable financing mechanisms developed and implemented (EE Strategy, 2005, EEAP 2010-2012, Law EE) | UNDP | 70,000 |  | 2,500,000 | Ministry for Economic Development and Ministry of Spatial Planning & Environment |
|  |  | UNECE | 20,000 |  |  |  |
| Renewable Energy Sources | Solar | UNEP |  |  |  | Ministry for Economic Development and Ministry of Spatial Planning & Environment |
|  |  | UNDP |  |  |  |  |
|  | Small Hydro PP | UNDP | 10,000 |  | 120,000 |  |
|  | Wood biomass | UNECE | 25,000 |  |  |  |
| Land use management and housing | Formalization of informal settlements UNDP- increasing EE of formalized settlements UNECE- energy efficiency in housing UNDP- energy governance and financial infrastructure, energy performance standards and technology integration, and access to EE and public housing | UNDP | 23,000 |  | 350,000 | Ministry of Spatial Planning & Environment |
|  |  | UNECE | 20,000 |  |  |  |
|  |  | UNDP | 12,000 |  | 400,000 |  |
|  | Capacity building | UNDP | 23,500 |  | 350,000 |  |
|  |  | UNECE |  |  |  |  |
| Strengthening environmental Health with focus on youth and children UNDP - analyzing impact of CC on human health | WHO |  |  |  | Ministry of Health |
|  | UNICEF |  |  |  |  |
|  | UNDP |  |  |  |  |
| Cleaner Production UNEP/UNIDO – in framework of joint Resource Efficient & Cleaner Production (RECP) program | UNIDO |  | 250,000 |  | Ministry for Economic Development |
|  | UNEP |  |  |  |  |
| CO2 Market (Institutional strengthening) | UNDP |  |  |  | Ministry for Economic Development |

| Pillar Outcome 3.2: | Established system for conservation and sustainable management of natural resources, effective prevention, control and reduction of environmental risks, and enhanced environmental awareness and participation by children, young people and adults. |
| --- | --- |
| Indicators & sources of verification System for conservation/sustainable management of natural resources and effective management of environmental risks established in line with the key national strategic documents, EU and UN requirements (Biodiversity Strategy and Action Plan, National Strategy for Sustainable Development, relevant national legislation, CBD, UNFCCC) Sources: Annual/Biannual progress reports on strategies’ implementation, EU progress reports, UN reports |
| National development priority Focus Area agreed with the government | Participating UN Agencies | Indicative budget (US$) 2012-16, by agency | Key Partners |
|  |  | Core | non-Core | Gap |  |
| Institutional and individual capacity building in BD conservation and management UNDP – learning platform for PA management UNEP (ENVSEC)- Durmitor and Prokletije establishment of transboundary protected areas UNESCO – translation and dissemination among Institutions and schools of UNESCO MAB learning materiel, and organization of biodiversity days and capacity-building seminars (teachers, protected area managers and trainers). | UNDP | 40,000 | 300,000 |  | Ministry of Spatial Planning & Environment |
|  | UNEP |  | 100,000 |  |  |
|  | UNESCO (Estimated total budget 250,000) |  | 50,000 |  |  |
| Effective prevention, control and mitigation of environmental risks (industrial waste management) UNEP will provide technical support and capacity building in connection to the remediation work developed by UNDP UNDP- remediation of hot spots | UNEP |  | 50,000 |  | Ministry of Spatial Planning & Environment |
|  | UNDP |  |  | 100,000 |  |
| Improved mechanisms for sustainable management of natural resources with focus on tourism industry. UNWTO: - Support establishing a policy framework to improve efficient use of resources (energy, water) as well as waste management in tourism sector, adapting tools for the industry, and creating incentives and policies to facilitate commitment from the private sector (Hotel Energy Solutions e-toolkit adaptation). - Assessment of the implementation of environment-related legislation in tourism destinations and in accordance with EU acquis communautaire. - Share best practices in the adoption the new technology and renewable energy in tourism business and destinations. - Identification of new opportunities for SMEs development in the resource efficiency technologies. | UNWTO |  |  |  | Ministry of Tourism and Ministry of Spatial Planning & Environment |
|  | UNEP |  |  |  |  |
| Development of key strategic documents in area of biodiversity (BD): UNDP- implementation of Biodiversity Strategy, Action Plan and National Report (BSAP). UNESCO: Expert support to the National Council for Sustainable Development (NCSD) for the review of the National Strategy for Sustainable Development (NSSD) promoting the integration of BD conservation and restoration in all relevant national policies. Development of indicators and coordinated plan of action. UNEP will support the development of necessary documents for the extension of existing protected areas for the establishment of transboundary ones. UNEP will support the development of National plans for the implementation of Convention on Biological Diversity (CBD) and relevant international agreements for the conservation of BD. | UNDP | 20,000 | 100,000 |  | Ministry of Spatial Planning & Environment, Ministry for Economic Development, Ministry for Agriculture, Water & Forestry, Ministry of Tourism |
|  | UNESCO (Estimated total budget: 150,000) |  | 20,000 |  |  |
|  | UNEP |  | 50,000 |  |  |
| Integrating BD in tourism, spatial planning and large infrastructural projects | Culture and development UNESCO: Elaboration of a Culture and Development strategy and action plans including cultural industry and tourism and environmental management. Further develop and implement the management plans and the action plans of the existing and candidate world heritage sites Kotor and Cetinje. UNDP- culture in function of reducing unemployment UNWTO- cultural tourism | UNESCO, | 140,000 |  |  | Ministry of Tourism and Ministry of Spatial Planning & Environment |
|  |  | UNDP | 50,000 |  |  |  |
|  | Protected area financing: UNDP - utilizing ecosystem service evaluation into management of public finances. A National Protected Area Financial Plan (NPAFP) is adopted A suite of regulatory instruments are in place to support implementation of the NPAFP | UNDP | 30,000 | 800,000 | 141,000 | Ministry of Tourism and Ministry of Spatial Planning & Environment |
|  | Protected Area management: UNDP- utilizing world heritage standards in local economic development: incentives, branding, quality control and promotion. UNESCO- utilizing world heritage standards in local economic development: incentives, branding, quality control and promotion. UNESCO: Continuation of SEDEP JP in Durmitor, developing the Stakeholders Platform for Durmitor WH site and Tara River Biosphere Reserve and contributing to the definition of a shared Action Plan considering not only conservation of heritage but fruition of the site for touristic purposes. In a second time, the UNESCO designated site should be used as a model/reference for better integration of nature conservation in Tourism and spatial planning at the national level (policy advise). UNWTO: Provide technical backing and guidance on how to integrate biodiversity in tourism, spatial planning and large infrastructural projects, using suitable elements and tools such as for instance the CBD Guidelines on Biodiversity and Tourism Development and user's manual and related UNWTO publications and Manuals UNEP- GIS as a tool for effective PA management | UNDP | 30,000 | 400,000 |  | Ministry of Tourism and Ministry of Spatial Planning & Environment |
|  |  | UNESCO (Estimated total budget: 450,000) | 50,000 |  | 100,000 |  |
|  |  | UNWTO | 10,000 |  |  |  |
|  |  | UNEP |  | 30,000 |  |  |
| Sustainable use and conservation of BD | Developing and marketing of participatory oriented, biodiversity based tourism products UNWTO: Application of methodologies and instruments for the design of biodiversity based tourism products. Participatory approach in which local communities are supported in managing their natural resources (Biodiversity) in a sustainable, non-consumptive way, aiming at the conservation of the biological diversity, sustainable use of biodiversity and equitable share of the benefits from the use of biodiversity. Horizontal cooperation organized from administrative local to district, departmental and national level; crosscutting subject, involving local authorities, nature conservation, forest, agricultural, infrastructure and other political sectors. | UNWTO | 20,000 | 500,000 |  | Ministry of Tourism and Ministry of Spatial Planning & Environment |

| Pillar Outcome 3.3: | Established system for strengthening entrepreneurial capacity building and facilitating private sector partnerships for ‘green jobs,’ rural livelihoods and development of Medium, Small and Micro Enterprises (MSME) in order to improve economic choices and achieve balanced regional growth as well as address gender specific concerns and interests. |
| --- | --- |
| Indicators & sources of verification System for entrepreneurial capacity building and development of SMEs established, with specific provisions to address gender specific concerns and interests, in line with the key national strategic documents (Regional Development Strategy, Strategy for SME development) Sources: Annual/Biannual progress reports on strategies’ implementation, EU progress reports, UN reports |
| National development priority Focus Area agreed with the government | Participating UN Agencies | Indicative budget (US$) 2012-16, by agency | Key Partners |
|  |  | Core | non-Core | Gap |  |
| Increasing competitiveness and diversifying income generation | “Green jobs” UNDP- increasing competitiveness of regionally based SMEs UNEP – support to the promotion of a greener sector/sub-sectors, including tourism, agriculture, Increased income and capacity for sustainable engagement. UNIDO-“green clusters” where environmental management practices (responsible use of resources such as water, energy, raw materials) will be promoted to reduce operating costs. UNWTO & ITC – build linkages with tourism consumption for productive capacities such as agriculture, crafts, supplies. | UNDP |  |  |  | Ministry for Economic Development, Ministry for Agriculture, Water & Forestry, Ministry of Tourism |
|  |  | UNEP |  |  |  |  |
|  |  | UNIDO |  |  |  |  |
|  |  | UNESCO |  |  |  |  |
|  |  | FAO |  |  |  |  |
|  |  | UNWTO | 20,000 |  | 400,000 |  |
|  |  | ITC |  |  |  |  |
|  | Establishment and strengthening of business clusters | UNIDO, UNDP |  |  |  |  |
|  | SME cluster and network development UNIDO- Competitiveness enhancement of MSMEs in Northern Montenegro through cluster and network development | UNIDO, UNDP |  | 250,000 |  |  |
|  | Women entrepreneurs | UNDP |  |  |  |  |
|  | ICT and SMEs | UNIDO |  |  |  |  |
| Public private partnership | Country specific PPPs projects | UNECE | 30,000 | 70,000 |  | Ministry for Economic Development |
| Corporate social responsibility | Responsible Entrepreneurs Achievement Program | UNIDO |  |  |  | Ministry for Economic Development |
|  | Global Compact UNIDO- Foster the development of socially and environmentally responsible and competitive SMEs | UNDP, UNIDO |  | 65,000 |  |  |
| Rural development | Developing agricultural value chain through fostering cooperatives FAO UNWTO & ITC – build linkages with tourism consumption for productive capacities such as agriculture, crafts, supplies. | FAO | 20,000 |  | 200,000 | Ministry for Economic Development, Ministry for Agriculture, Water & Forestry, Ministry of Tourism |
|  |  | UNIDO |  |  | 400,000 |  |
|  |  | UNWTO |  |  |  |  |
|  |  | ITC |  |  |  |  |
|  | Technical assistance to SMEs UNDP - ‘Sustainable Tourism for Equal Chances’ (EC) | UNDP | 0 | 52,000 |  |  |

# Footnotes

Based on agency programme and financial management information (e.g. Atlas, ProMS, etc)

Based on Phase I Budgetary Framework (the total of core and non-core resources)

Based on agency programme and financial management information (e.g. Atlas, ProMS, etc)

Based on Phase I Budgetary Framework (the total of core and non-core resources)

Based on agency programme and financial management information (e.g. Atlas, ProMS, etc)

Based on Phase I Budgetary Framework (the total of core and non-core resources)

Second phase of the ongoing UNIDO project

UNWTO: Current value of HES tools, available for adaptation, is US$1.5M

‘Green Jobs’ are defined as positions in agriculture, manufacturing, R&D, administrative, and service activities aimed alleviating the myriad environmental threats faced by humanity.  Specifically, but not exclusively, this includes jobs that help to protect and restore ecosystems and biodiversity, reduce energy consumption, de-carbonize the economy, and minimize or altogether avoid the generation of all forms of waste and pollution (UNEP)