### Country:		UKRAINE

### COUNTRY PROGRAMME PERFORMANCE SUMMARY

### Reporting period: 	2006-2011

### I.  EXECUTIVE SUMMARY

The UNDP Country Programme for Ukraine for 2006-2010 extended till the end of 2011, was aimed to support the Government in its efforts to achieve European standards of living through a new wave of policy reforms, institutional capacity development and implementation of innovative demonstration projects. In consultation with the Government of Ukraine UNDP undertook to prepare ground for decentralisation reform though supporting local self-help initiatives and promoting examples of positive engagement between the citizen and state authorities. The role of civil society in sound economic governance was enhanced through improved public access to consumer rights/economic empowerment information and capacity building of consumer CSOs. UNDP worked to increase the effectiveness of social services for unemployed with particular focus on the needs of persons with disabilities. UNDP supported Government's effort to develop a multi-sectoral approach to HIV prevention and care programmes. UNDP’s position in the Autonomous Republic of Crimea (ARC) was strengthened though strategic dialogue with ARC authorities and the establishment of donor coordination mechanism on the ground. Through supporting a nation-wide civil society development programme UNDP assisted medium sized- and small regional NGOs to work jointly in addressing human rights violations of specific vulnerable groups. UNDP implemented two area-based development programmes in the Autonomous Republic of Crimea and in areas affected by the Chernobyl accident of 1986. It contributed to reducing poverty and inequality and thus increased human security of the population. UNDP worked to further promote sustainable resource management, energy efficiency and biodiversity. UNDP has been assisting the Government of Ukraine in monitoring of progress towards Millennium Development Goals and setting new targets integrated into various state strategies and programmes. UNDP has published regular updates on the progress of reforms (Blue Ribbon Commission Reports) and analysis of the European governance standards and consistency of the human development agenda with European integration requirements (National Human Development Report 2008 on Human Development and Ukraine's European Choice).

UNDP provided capacity development support to the government in view of its WTO accession. As a result, Ukraine entered in WTO in May 2008, with increased capacity of government officials to conduct negotiations in the implementation phase. UNDP has enhanced national capacities for inclusive participatory planning at local and regional level. All 27 regions of Ukraine received training on participatory planning and decentralized service delivery. In order to ensure sustainability, UNDP supported establishment of municipal and regional resource centres based in state and local administrations. 15 executive bodies and 17 regions were trained on gender-sensitive planning. As a result, 9 ministries have developed gender action plans and 27 regions have developed gender plans with resources from regional budget.

UNDP provided targeted assistance to support Ukraine’s European integration process, officials of the cabinet of ministers participated in two study tours to Slovakia to learn successful models of horizontal coordination of European integration process. The Main Department of Civil Service (MDCS) was supported in drafting of the law on civil service and establishment of a School for High Civil Servants in the structure of the MDCS. Though supporting a nation-wide Civil Society Development Project, UNDP assisted the civil society organizations in addressing human rights violations of specific vulnerable groups. UNDP worked with CSOs, journalists and judges to increase awareness and effectiveness in pursuing consumer-rights related cases.

The key partnerships and inter-agency collaboration include:

- Partnership with the Cabinet of Ministers, through establishment of national focal point for Community-Based Approach to Local Development, was crucial for scaling up of local development programmes.

- Partnership with the Vice Prime Minister and the European Integration Bureau was instrumental to ensure impact for the NHDR.

- Cooperation with the WB, UNICEF, ILO, IMF on the international conference on poverty alleviation (April 2008), which produced policy recommendations for the Government of Ukraine.

- Joint Programme with ILO was launched on employment of people with disabilities; implementation of joint projects with UNFPA and UNICEF on HIV/AIDS continued.

- Partnership established and a new project on Youth Inclusion was launched with Intel, Min. of Family Youth and Sport, Min. of Education, Ukraine-3000, Alternative-V, UN Volunteers

- Partnership with the EC was expanded, in particular opening of new areas of cooperation in areas of core UNDP interest and competence (gender, local development, Crimea).

### II: Country Programme Performance Summary

| Country information |  |
| --- | --- |
| Country name: Ukraine |
| Current country programme period: 2006-2011 |
| Outcomes | Total Expenditure | Key Indicators of outcome (1-4 per outcome) | Progress made against key indicators |
| Accountable citizen-based government promoted. | $69,337,994 | Public trust in and access to government services and support at higher levels. Baseline: Low level of trust/ perception Target: High level of trust (50% and above) | Political instability resulted in the decreased trust of the population in the government. Quality management system of municipal services piloted and introduced in at least 1% of Ukrainian municipalities. Border crossing procedures for individuals streamlined. |
| UNDP Contribution: CP Outputs: Public administration reform and public access to government strengthened through institutional reforms and anti corruption measures. Progress and Achievements: Though the first report of Blue Ribbon Commission launched in January 2005, UNDP provided advice on the set of governance reforms necessary for improvement of the relationship between the citizen and state. In support of implementation of the Millennium Challenge Corporation Threshold Country Programme in Ukraine, UNDP worked with the Cabinet of Ministers and the Secretariat of the President of Ukraine to facilitate better coordination of activities and organisations implementing anticorruption projects with the Parliament and the Executive branch in Ukraine. UNDP, together with the other UN agencies, contributed to the development of the Law Against Corruption which was approved in 2009. UNDP has actively supported the reform process by assisting to the functional reviews of governmental executive bodies; supporting the establishment of the School for Senior Civil Servants and the development of Senior Civil Service Formation and Management Concept; advocating for the change of law on civil service through a number of targeted and high-level advocacy initiatives. Following the Presidential and local elections as well as Constitutional reform Ukraine witnessed a period of important changes in the governance architecture, i.e. formation of a stronger presidential power. The relative political stability created an opening for the long-awaited public administration reform which was launched in December 2010. In support of the anti-drug trafficking effort, UNDP implemented a project of cooperation between customs, border guards, intelligence services and public health authorities of three countries (Belarus, Moldova and Ukraine) and strengthened their links with their EU counterparts in preventing and effective response to drug trafficking. Responding to the request of the European Commission, UNDP has been acting as implementing partner for the EU Border Assistance Mission to Moldova and Ukraine and provided financial, administrative, procurement and human resource management service to the EUBAM. UNDP through EUBAM has also provided technical and expert support to the development of the Integrated Border Management concept adopted by the Cabinet of Ministers of Ukraine in 2010. |
| 2. Access to justice and human rights improved. | $11,711,665 | Human rights and justice become corner stone of government policy and practice. Baseline: Status as per UNHCHR* Report in 2005 Target: Gaps identified in UNHCHR Report acted upon for full compliance. | Ukraine is a signatory to most multilateral human rights instruments. The International law of human rights forms an integral part of the legislation of Ukraine. Meeting its international obligations and adherence to international law has been regarded as a priority by the Government. The Ukrainian Parliament ratified the UN Convention on the Rights of Persons with Disabilities in 2009. |
| UNDP Contribution: CP Outputs: a) Institutional arrangements and capacities of the Ombudsperson Office, Parliament and civil society organizations developed for citizen access to human rights; b) Access to justice and rights enhanced through reforms and strengthening of the judicial system, court administration and the media. Progress and Achievements: Supporting the initial priorities announced by the President in 2005 in the area of justice sector reform, UNDP contributed to preparation of a white paper on justice sector reform and provided advisors to work as part of the National Commission on Justice and the Rule of Law. While supporting implementation of recommendations of the commission, UNDP assisted the establishment of administrative courts and worked with the Academy of Judges and State Court Administration to increase their institutional capacity. In Crimea, UNDP worked with the local authorities and Crimean Tatar representatives on multi-language education and tolerance promotion at schools. Responding to the need for equality of men and women and protection of women's rights in the workplace, UNDP worked with the Ministry of Family, Youth and Sports and a range of other central and regional government institutions and assisted them in introducing the function of gender focal points in every state structure. UNDP experts provided training and advisory services to assist national counterparts in preparation of work plans and monitoring tools for the above gender machinery. Focusing on the problem of domestic violence against women and children, UNDP worked with NGOs and Government agencies to diagnose institutional and legal problems that need to be addressed and provided training opportunities to the staff of the Ministry of Interior. In addition, UNDP worked with the Ministry of Education and Science to review school curricula and revise any gender biased content. The development of the gender national mechanism received a new impulse in 2010 and demonstrated strong national ownership by the Ministry of Family, Youth and Sports: the new Department for Family and Gender Policy with a specialised division of gender policy was established, amendments to 11 Laws of Ukraine to advance women’s agenda were elaborated, the new State Gender Equality Programme for 2011-2015 was drafted, a gender adviser to the Prime Minister of Ukraine was appointed, the Expert Council for addressing of sex discrimination cases was set up. All these initiatives were carried out in line with UNDP recommendations provided to the Government. 2010 also witnessed the establishment of the first departments on gender studies in 5 leading Universities with the support provided by UNDP. Despite these efforts there has been still little progress in achieving MDG targets on gender equality in 2010. The number of women in the Parliament and the Cabinet of Minister as well as the income gap between men and women are still significantly lagging behind the national MDG target. |

| 3. People-centred decentralization and local public governance. | $32,311,121 | Progress in MDG Targets. Baseline: MDG levels at 2005 as given by Ministry of Economy Target: Progress on most targets achieved | Ukraine has reduced the absolute poverty from 9 percent in 2005 to 4.5 percent in 2009, however the relative poverty measure according to the nationally defined poverty line has remained stable at the level of 27 percent. Most of the targets in the education goal and the goals on maternal health and child mortality have been successfully reached. Representation of women in the Parliament at 8% is very low . |
| --- | --- | --- | --- |
| UNDP Contribution: CP Outputs Decentralized institutional arrangements for local governance developed and citizen-based partnerships for participatory development promoted Progress and Achievements UNDP promoted the idea of self-governance and decentralisation and worked with representatives of local authorities across Ukraine to increase their knowledge of the reform and readiness to take on new responsibilities. Through a nation-wide network of over 2,000 mini-projects working on the level of rural and municipal communities, UNDP piloted mechanisms of community-based planning and priority setting and demonstrated concrete solutions in improvement of basic local infrastructure and access to services. In cooperation with local communities, 24 regional administrations and the Autonomous Republic of Crimea, over 200 districts and 28 municipalities, UNDP has been building capacity for self-governance and helped to create community organisations which cooperate effectively with local authorities. Projects at the community level included energy efficiency in local schools, kindergartens and health care facilities, improvement of local basic health care infrastructure, access to water, gasification, school buses and environmental initiatives. The success of community projects triggered requests from the Government to UNDP Ukraine to discuss the policy obstacles for wide implementation of community-driven initiatives. Knowledge gained from the UNDP local development projects implementation provided basis for the development of policy recommendation to enable participatory local governance in Ukraine. In addition to the policy recommendations on decentralization, recommendations to the Ministry of Housing and Municipal Economy of Ukraine on housing reform and development of training course on creation and functioning of associations of co-owners of multi-apartment houses were elaborated; recommendations on solid waste management systems in municipalities and role of urban population in separate waste collection were developed and discussed with key local and government stakeholders. UNDP supported the elaboration of the State Programme to Support of Small Cities Development which was adopted by the Government of Ukraine. UNDP engaged in municipal development programmes with 30 municipalities that contributed in total about 3 mln dollars from their budgets. Despite significant reduction of budget resources as a result of financial crisis, municipalities continued to contribute resources to UNDP projects. In promotion of dialogue and civic participation, in cooperation with the Parliament of the Autonomous Republic of Crimea and the Crimean Tatar leadership, UNDP helped to establish the Crimean Human Security Council which has become a forum for open discussion of various development issues in Crimea. UNDP supported and facilitated the process of elaboration, discussion and approval of local development strategies of 4 Crimean districts. Two rounds of large-scale public hearings on elaborated strategies with participation of over 5200 local residents were facilitated. |
| 4. Civil society organizations protect and advocate for human rights and justice. | $7,197,913 | Equal access to services achieved. Baseline: Level of family violence in 2005. Target: Decline in family violence by 50% in 2010. | A number of by-laws were adopted thus ensuring proper statistics collection on family violence. As a result, the number of registered cases increasedby 20%. Networks of social centers for assistance and rehabilitation of the victims of family violence were established by the State in all regions of Ukraine. |
| UNDP Contribution: CP Outputs: Access to equal opportunities and justice, with focus on women and disadvantaged groups, increased through capacity building of NGOs/CBOs in partnerships with local authorities/government. Progress and Achievements: In the area of civil society development the strong potential of the CSOs remains restricted by an outdated legal framework. Though supporting a nation-wide Civil Society Development Project, UNDP has been helping medium sized- and small regional NGOs to work jointly in addressing human rights violations of specific vulnerable groups. In support of implementation of a project of the UN Democracy Fund, UNDP cooperated with regional CSOs in conducting human rights and civic education trainings for locally elected officials in Western Ukraine. Working with CSOs and the policy and decision makers, UNDP contributed to the development of draft law on civil society organisations. UNDP keeps supporting CSOs efforts to lobby for the changes in the respective legislation and enhances CSOs’ capacities in inclusive policy decision making. In response to the needs of organisations and experts working in the area of consumer rights protection, UNDP created a new consumer rights portal, created educational programmes, conducted media and outdoor information campaigns and established a hotline for referral of consumer claims. UNDP worked with CSOs, journalists and judges to increase awareness and effectiveness in pursuing consumer-rights related cases. |
| 5. Leaders actively engage and spread of HIV/AIDS begins to decline. | $6,704,764 | Stability in spread and decline tendencies in HIV/AIDS Baseline: % of population affected in 2005. Target: % decline in population affected in 2010. | The number of new cases of HIV-infections per 100,000 people has more than tripled since 2000. The estimated adult prevalence of HIV infection is 1.33%, the estimated number of people living with HIV is 360,000 and the estimated number of AIDS related deaths is 21,000 per year. However, the proportion of young people among the newly reported cases of HIV is decreasing. |
| UNDP Contribution: CP Outputs: a) Prevention of HIV/AIDS scaled-up through capacity building of leaders and multi-sectoral and multi-institutional oriented responses; b) Access to prevention and care for vulnerable groups, such as youth, injecting drug users, commercial sex workers, and people living with HIV/AIDS enhanced. Progress and Achievements: Ukraine remains the most hit by the HIV epidemic country in Europe. The amount of new HIV infection cases reached 44 per 100,000 at the end of 2010. However, the proportion of young people among the newly reported cases of HIV is decreasing. In order to scale-up the response to HIV/AlDS and ensure involvement of all relevant government institutions, UNDP assisted the Ministry of Labour and Social Policy, private sector companies and the Ministry of Transport in elaboration of action plans and capacity development activities. Building on the network of contacts on sub-national level, UNDP worked with the National HIV/AIDS Committee to increase their capacity to work with regions of Ukraine and support local efforts on HIV prevention and treatment. UNDP provided assistance to the National HIV/AIDS Committee in preparation of the country proposal to the Global Fund grant, Round 10 as well as facilitated the efforts of the State in decreasing cost of the antiretroviral medicines through assisting in amending the legislation to ensure better access to medicines. Another achievement was organization and hosting of the Regional Workshop on intellectual propriety rights and access to medicines. Strong emphasis was made on decentralization of the response to HIV/AIDS with the capacity building of the regional HIV/AIDS councils in 3 regions. In addition, UNDP established a forum of the key stakeholders involved into activities at the sub-national level and sponsored the HIV/AIDS response analysis of two regions. It kept mainstreaming HIV/AIDS into the uniformed, supporting improvement of skills and knowledge in HIV/STI prevention of 500 staff dealing with the human resources policy/management and info-educational sector in remote military settlements. UNDP worked on extension of the network on monitoring and response to human rights violations; conducted the information campaign on tolerance for youth; supported capacity development of Prisons Department officers and judges and released a Guidebook on HIV and Human Rights for judges. UNDP influenced the anti-epidemic measures through assisting the estimation of the cost of the national response to HIV/AIDS and suggestion for direct financing of the HIV/AIDS programmes. Human-rights based approach to addressing HIV/AIDS problem was promoted by inclusion of new 5 regions into the human rights monitoring network and commencing monitoring activities in the context of HIV/AIDS among men having sex with men (MSM). A significant number of activists were trained in human rights and HIV/AIDS; data of the research on needs of MSM regarding HIV/AIDS were presented at the first National AIDS Conference and the Regional Consultation “HIV: Hidden Epidemic among MSM and Transgender in EECA” held in 2010. |
| 6. Sustainable economic development through pro poor policy reform. | $7,783,007 | Decline in rural and urban poverty through equitable income and new environment of cooperation of state, enterprises and civil society. Baseline: Level of rural and urban poverty in 2005(absolute-9,0%, national criterion – 27,1%) Target: Ukrainian MDG target on poverty achieved by 2010 | Ukraine has managed to reduce the absolute poverty to 4.5 percent; however, the relative poverty has remained stable at the level of 27 percent, which is 2% above the national MDG target. The poverty level in rural areas is almost twice as high as in urban areas (38.2 percent against 21.5 percent). |
| UNDP Contribution: CP Outputs: a) Agriculture and rural development policy reform further strengthened and access of Ukrainian farmers to property, credit schemes, technology and market services enhanced; b) New wave of social and economic policy reform at the national and regional levels implemented; and small and medium enterprises expanded through area-based poverty alleviation initiatives. Progress and Achievements: In supporting Ukraine's poverty reduction effort, UNDP worked on the central and local level, in particular in the Autonomous Republic of Crimea, to assist Ukrainian farmers in creating cooperatives, gaining better position on the market and accessing financing for their local agricultural enterprises. UNDP worked closely with the Government of Ukraine and provided analytical input and expert advice in the process of WTO accession. Experts of the UNDP founded Blue Ribbon Analytical and Advisory Centre provided direct consultation to a range of government agencies on a broad range of macroeconomic issues including fiscal and regulatory policy, international trade and pensions system reform. UNDP conducted the analysis of post-WTO accession impact, supported the elaboration of the national medium- and long-term development plans, and contributed to the improvement of corporate legislative framework. In cooperation with the Government, private sector as well as UNICEF, ILO, WB and IMP, UNDP organised a national conference on poverty and issued a poverty assessment report. UNDP undertook also innovative work to assess the degree of social exclusion in Ukraine, thus helping the national counterparts to adapt their approach to poverty measurement and poverty reduction to the European social inclusion policy standards. In areas affected by the Chornobyl accident, UNDP organised business forums and supported establishment of one-stop-shops for SMEs thus contributing to development of local private sector and building the sense of normalcy and self-reliance of local communities. UNDP continued to support the Government to accelerate the achievement of the national MDGs. Specifically, UNDP assisted the Ministry of Economy in carrying the mid-term review of the national MDGs, and the preparation of updated system for monitoring of the MDG targets. A National MDG report was presented by the President of Ukraine at the 65th UN General Assembly, reaffirming the Government commitment to achievement of the MDGs. The revised system of MDG targets and indicators became the platform for building consensus for further national development. UNDP also supported the analysis of economic crisis consequences on poverty in Ukraine which became the sound base for elaboration of a new strategy on poverty alleviation. The Model for provision of employment services to people with disabilities, developed in 2009 with the support of UNDP and ILO, was piloted in several regions of Ukraine in 2010 and the results revealed by the government employment centres where the Model was piloted showed the increase in employment of people with disabilities from 25 to 40 percent. |
| 7. Human security enhanced through recovery and development. | $355,832 | Government incorporates human security as fundamental policy. Baseline: Practice demonstrated 2005 Target: Policy prepared and budget | Government Disaster Risk Reduction Strategy developed. Influenza outbreak situations communication strategy developed by the Ministry of Health. |
| UNDP Contribution: CP Outputs: Human security responses, with attention to the youth, Crimea, Chernobyl and other vulnerable regions consolidated, up-scaled or promoted. Progress and Achievements: UNDP established close partnership with the Ministry of Emergencies and other relevant counterparts responsible for influenza preparedness planning, assisted in preparation of the national contingency plan and supported the donor coordination effort. In response to floods that affected Western Ukraine in 2008, UNDP and the UN CT helped the Ministry of Emergencies to conduct capacity assessment and prepare disaster risk reduction strategy and a set of demonstration projects and funding proposals which were then presented to international counterparts and donors. UNDP focused its efforts on raising the government capacities in disaster preparedness and risk reduction. The UN and the EU collaborated with the Ministry of Emergencies and conducted a rapid assessment in the Western part of Ukraine, in the city of Kalush where Persistent Organic Pollutants were not contained and recommended urgent measures to save people and the environment. As a result of the timely intervention, the Government allocated funding to prevent the anthropomorphic disaster in Kalush. |
| 8. Sustainable development policies and practices make the difference. | $7,958,403 | Decline in green-house gas/carbon dioxide emission and stability in rate of deforestation. Baseline: % green gas emission per capita and minimization of natural disasters Target: 50% decline in green gas emissions per capita and non-occurrence of floods and natural disasters due to sound forest practices | Ukraine is a leader in number of JI projects (29) accounting for 45.3 m Emission Reduction Units generated. UNDP efforts to mobilize donor and government resources and support programs on introducing sound forest practices were not successful. |
| UNDP Contribution: CP Outputs: a) Institutional capacities and capabilities of municipalities strengthened through improved policies and practices related to energy services and environment.; b) Sustainable governance and management of natural and biodiversity resources promoted through capacity building and regional cooperation. Progress and Achievements: In the area of energy efficiency and environmental protection UNDP assisted municipalities and regional authorities in introducing energy efficiency in municipal heating system, landfill utilisation and transport management. UNDP developed an educational programme for primary and secondary schools on energy conservation and developed models of energy efficiency improvements for three basic types of Ukrainian schools (large, medium and rural school). UNDP worked with a group of experts and NGOs to prepare the National Environmental Policy and Energy Security Assessment. The policy document is based on the evaluation of the national ecological potential and aims at providing key recommendations for its further development. UNDP is active in assisting the Government of Ukraine and the regional and municipal authorities in applying the Kyoto Protocol mechanisms, particularly on raising awareness and building in-country expertise for identification and development of Joint Implementation projects in Ukraine. Ukraine is the first country to implement a project under the MDG Carbon Facility in the city of Lugansk. To address a key issue in the reduction of greenhouse gas emissions, UNDP supported the implementation of an innovative pilot public-private partnership mechanism for energy efficiency at municipal level – ESCO. The project improves energy efficiency of communal heating facilities and strengthens capacities at the local level. ESCO-Rivne municipal company, established on the basis of an ESCO modality, introduced internationally recognized model for performing energy audit for municipal clients – investment-grade energy audit. Significant progress was made in the area of natural reserves and national parks and the total area of protected territories increased twice (from 4.6% to 9% of the overall territory of Ukraine). The number of national parks was also increased twice (from 18 to 36). UNDP supported the establishment of an Association of Protected Areas as a platform for knowledge exchange and transfer of experience between protected areas (PAs). One and a half years of Association’s work led to the development of a National Strategy on the Protected Areas’ Financial Sustainability and provided access to world best practice in business planning and ecotourism to more than 217 nature protection practitioners. UNDP, in partnership with the Global Compact network companies was also involved in initiating a national information campaign on environment and energy efficiency and supported the first Business Summit on Climate Change. |
| Please add rows above for additional outcomes as appropriate |
| Summary of evaluation findings (e.g. from outcome and project evaluations, UNDAF reviews, and other assessments) In 2008, a UNDAF mid-term review was conducted to assess the continued relevance of the UNDAF as a strategic document, to identify gaps and to introduce required modifications. In this context, a mid-term Country Programme Action Plan review was also conducted. The mid-term review found that the overall programmatic approach proposed by the CPAP and employed by UNDP in the period 2006-2008 remained valid and relevant to the national context and that UNDP had made progress in implementation of the main outputs. The review provided recommendations on how UNDP can best position itself and maximise impact of its programming in the last two years of CPD implementation and continue fostering national capacities, in the context of the global recession. Readjustments to the implementation strategy were made to respond to new development challenges including the global economic crisis. Thematic Evaluation of UNDP’s Contribution to Decentralization and Strengthening Local Governance (2000-2009), which analyzed UNDP Ukraine experience in Local Governance field as a case study, stated that UNDP Ukraine’s creation of a local development strategy and adoption of a CBA has clearly been successful in a number of areas. An outcome-based evaluation of Democratic Governance portfolio is in the process of preparation and the report is expected to be ready by the end of March 2011. Key Achievements: Expansion of the local development programme to cover all regions, enabling UNDP to replicate its successful approach country-wide and ensure even capacity development for participatory governance at local level. The UNDP Equal Opportunities Programme was scaled up with a major contribution by the European Commission, and is now the largest gender programme in the RBEC region. The National Human Development Report “Human Development and Ukraine’s European Choice” was launched in 2008, as a tool for policymakers to formulate a cohesive agenda for reform towards European approximation, which is inextricably tied to human development indicators. UNDP promoted modern approaches in landscape and biodiversity conservation, by developing a full size project document which obtained GEF funding. Among the achievements is the established National Association of Protected Areas. A National MDG report including mid-term review of the MDGs, and updated system for monitoring of the MDG targets was prepared and presented by the President of Ukraine at the 65th UN General Assembly, reaffirming the Government commitment to achievement of the MDGs. UNDP promoted sustainable local development of the Chernobyl-affected areas, provided scientifically-sound information on radiation and healthy life style, empowered affected individuals and communities to get rid of the ‘Chernobyl victim’s syndrome and to play more active roles in improving their local living conditions. Major Lessons Learnt: The general lessons learned for UNDP's future programming in Ukraine are that: by investing relatively small resources at the local level, UNDP achieves relatively larger impact and visibility than acting on the central level. Also, at the time of political instability, the donor community focuses attention on activities at regional and local level which allows presenting results of successful projects and often attracting funding for their expansion. by diversifying partners and brokering innovative and dynamic partnerships, UNDP achieves bigger development impact and succeeds to stay at the forefront of Ukraine’s development agenda. providing technical advice and assistance on local level is not sufficient to achieve long-term development impact. It is crucial that the local governments (municipalities) and other local actors such as the private sector also take the responsibility to invest both financially from their financial resources as well as take the leadership in bringing the local stakeholders together to enhance the development process. |

III. Country Programme Resources

| Focus Area | Programme Expenditure ($) | % of Total |
| --- | --- | --- |
|  | Regular (TRAC) | Other | Total |  |
| Poverty and MDGs | 3 177 000,0 | 11 323 771,0 | 14 487 771,0 | 10,1 |
| Democratic Governance | 10 209 000,0 | 110 646 693,0 | 120 558 693,0 | 84,1 |
| Crisis Prevention and Recovery | 355 832,0 | 0,0 | 355 832,0 | 0,2 |
| Environment and Sustainable Development | 336 000,0 | 7 622 403,0 | 7 958 403,0 | 5,6 |
| Total | 14 077 832,0 | 129 592 867,0 | 143 360 699,0 | 100,0 |

Data sources: (please indicate the main sources from which data were obtained for this report.)

UNDAF (2006 – 2010) mid-term review Country Programme Action Plan (2006 – 2010) mid-term review National Report on MDGs Ukraine 2010 UNDP outcome and project evaluation reports 2008, 2009, 2010 Result Oriented Annual Reports Annual Strategy Notes

# Footnotes

Including EU Border Assistance Mission totaling to USD 79 290 000