**ANNEX**. **FULLY-COSTED EVALUATION PLAN – TRINIDAD AND TOBAGO 2022-2026**

The Multi-Country Office recognizes the importance of monitoring and evaluation in programme management. In its attempt to assess programmatic effectiveness the MCO has developed an evaluation plan for the period 2022-2026, focusing on the MSDF areas of i)*“Equality and Well-being”* and ii)*“Resilience to Climate Change and Sustainable Resource Management”*. The choice of evaluations to be conducted within the period were chosen based on relevance to the attainment of Country Programme Document (CPD) outcomes, available funding, and whether the projects fell within the criteria for mandatory evaluations. It should be noted that the list of planned evaluations as presented below will not be limited to those identified in plan. The MCO will reserve the right to append additional evaluations to the plan over the course of the CPD period if other evaluations arise due to pipeline projects coming to fruition. As an NCC Country Office with limited dedicated resources available for the purpose of monitoring and evaluation, the MCO has decided, at this time, to omit from the evaluation plan any thematic or outcome evaluations. However, the MCO will reconsider this decision if over the course of the 2022-2026 programmatic period funding sources become available that would allow for a comprehensive outcome evaluation.

|  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **UNDAF (or equivalent)****Outcome**  | **UNDP Strategic Plan Outcome** | **Evaluation Title** | **Partners (joint evaluation)** | **Evaluation commissioned by (if not UNDP)** | **Type of evaluation** | **Planned Evaluation Completion Date** | **Estimated Cost** | **Provisional Source of Funding** |
| MSDF Area: People- Equality and well-being (Leave No One Behind) | Outcome 2. Accelerate Structural Transformations for Sustainable Development | Project Evaluation: Building a Nation: Sint Maarten NDP and Institutional Strengthening | Ministry of General Affairs, Department of Interior and Kingdom Relations (BAK) | UNDP | Project Evaluation | April 2022 | USD15,000 | Office M&E Budget  |
| MSDF Area:Planet- Resilience to Climate Change and Sustainable National Resource Management | Outcome 2. Accelerate Structural Transformations for Sustainable Development | Project Evaluation: Global Climate Change Alliance + | Ministry of Planning and Development; Ministry of Energy and Energy Industries | UNDP | Project Evaluation | June 2023 | USD25,000 | Project budget |
| MSDF Area:Planet- Resilience to Climate Change and Sustainable National Resource Management | Outcome 2. Accelerate Structural Transformations for Sustainable Development | Mid-term Project Evaluation: Aruba SISSTEMS Faculty Initiative | Department of Economic Affairs, Commerce and Industry; Department of Public Works; Monuments Bureau of Aruba; University of Aruba  | UNDP | Project Evaluation | March 2022 | USD12,000 | Project budget |
| MSDF Area:Planet- Resilience to Climate Change and Sustainable National Resource Management | Outcome 2. Accelerate Structural Transformations for Sustainable Development | Final Project Evaluation: Aruba SISSTEMS Faculty Initiative | Department of Economic Affairs, Commerce and Industry; Department of Public Works; Monuments Bureau of Aruba; University of Aruba | UNDP | Project Evaluation | October 2022 | USD12,000 | Project budget |
| MSDF Area:Planet- Resilience to Climate Change and Sustainable National Resource Management | Outcome 2. Accelerate Structural Transformations for Sustainable Development | Final Project Evaluation: Energy Efficiency through the Development of Low Carbon RAC Technologies in Trinidad and Tobago (GEF 6)   | Ministry of Planning and Development | UNDP | Project Evaluation | June 2025 | USD25,000 | Project budget |
| MSDF Area:Planet- Resilience to Climate Change and Sustainable National Resource Management | Outcome 3. Strengthen Resilience to Shocks and Crises | Final Project Evaluation: Community Flood Early Warning System (CFEWS) project | Office of Disaster Preparedness and Management;  | UNDP | Project Evaluation | June 2024 | USD10,000 | Project budget |