___________________________________________________________________

Republic of Kenya 						          ___________________________________________________________________

ECONOMIC EMPOWERMENT PROGRAMME

# MID-TERM REVIEW REPORT (DRAFT)

# JULY 2014 – JUNE 2016

UNITED NATIONS DEVELOPMENT PROGRAMME

&

MINISTRY OF DEVOLUTION & PLANNING

__________________________________________________________

### BY

JULIUS MBURUGU, LEAD CONSULTANT

0722218950; juliusmburugu@yahoo.com

&

LOISE OBURU, ASSISTANT CONSULTANT

O720141274; oburuloise@gmail.com

NAIROBI, KENYA

DECEMBER 2016

|  | TABLE OF CONTENTS | 2 |
| --- | --- | --- |
|  | ABBREVIATIONS AND ACCRONYMS | 3 |
| 1.0 | PROGRAMME BACKGROUND | 5 |
| 1.1 | Kenya’s National Priorities and Socio-economic Challenges | 5 |
| 1.2 | The Economic Empowerment Programme | 6 |
| 1.3 | Programme Management Arrangements | 7 |
| 1.4 | Purpose, objective and scope of the Assignment | 8 |
| 1.5 | Review Methodology | 8 |
| 1.6 | Limitations of the Review | 9 |
| 2.0 | REVIEW OF ACHIEVEMENTS AND KEY ISSUES | 10 |
| 2.1 | Key Findings | 10 |
| 2.2 | Key issues that have hindered achievement | 12 |
| 3.0 | WEAKNESSES AND STRENGTHS OF PROGRAMME DESIGN (including financial) | 12 |
| 3.1 | Project Strategy – Project design, Results Framework/Log frame | 13 |
| 3.2 | Progress towards Results- Progress towards Outcomes Analysis | 13 |
| 3.3 | Performance Review | 14 |
| 4.0 | KEY RECOMMENDATIONS | 16 |
| 5.0 | LESSONS LEARNT AND BEST PRACTICES | 16 |
| 6.0 | REFERENCES |  |
| 7.0 | ANNEXES |  |
| 7.1 | Annex 1: Aide Memoire |  |
| 7.2 | Annex 2: Documentation of Proposed Changes |  |
| 7.3 | Annex 3: Interviews and Visits Itinerary | 17 |
| 7.4 | Annex 4: Biashara Centre Training Activities |  |
| 7.5 | Annex 5: Enrolment in Supported Vocational Training Centres |  |
| 7.6 | Annex 6: Terms of Reference |  |

ABBREVIATIONS AND ACRONYMS

AGPO		: 	Access to Government Procurement Opportunities

AWP		:	Annual Work Plan

BDS			Business Development Services

BS		:	Business Skills

BS&ED	:	Business Skills and Entrepreneurship Development

BCtA		:	Business Call to Action

CBD		:	County Business Development

CIDPS		:	County Integrated Development Plans

CPD		:	Country Programme Document		:

CSOs		:	Civil Society Organization

DVET		:	Department of Vocational Education Training

EEP		:	Economic Empowerment Programme

GDP		:	Gross Domestic Product

GOK		:	Government of Kenya

HFF		:	Housing Finance Foundation

HIV		: 	Human Immunodeficiency Virus

ICT		:	Information Communication Technology

IOM		:	International Organization for Migration

IP		:	Implementing Partner

KAM		:	Kenya Association of Manufacturers

KENIVEST	:	Kenya Investment Authority

KEPSA	:	Kenya Private Sector Alliance

KNCCI	:	Kenya National Chamber of Commerce and Industry

MoALF	:	Ministry of Agriculture, Livestock and Fisheries

MoEST	:	Ministry of Education, Science & Technology

MOUs		:	Memorandum of Understandings

MSE 	: 	Micro and Small Enterprises

MSEA		:	Micro and Small Enterprise Authority

MSMEs	:	Micro, Small and Medium Enterprises

MTP		: 	Medium Term Plan

MTR		:	Mid-Term Review

NITA		:	National Industrial Training Authority

OSIC		:	One Stop Investment Centre

PRODOC	:	Programme Document

PSC			Project Steering Committee

SDGs		:	Sustainable Development Goals

SMART	:	Specific, Measurable, Achievable, Realistic, Time-bound

SME		:	Small and Medium Enterprise

UN		:	United Nations

UNDAF	:	United Nations Development assistance Framework

UNDP		:	United Nations Development Programme

UNV		:	United Nations Volunteer

VTC		:	Vocational Training Center

YEF		:	Youth Enterprise Facility

YEDF		:	Youth Enterprise Development Fund

YP		:	Youth Polytechnic

1.0	PROGRAMME BACKGROUND

  - Kenya’s National Priorities and Socio-economic Challenges

Under Vision 2030, Kenya aims to be a middle-income rapidly industrializing country by 2030, offering all its citizens a high quality of life. Studies have shown that micro, small and medium-sized enterprises (MSMEs) (UNDP, 2015) generate roughly 85% of employment and 20% of GDP in Kenya.  Linkages between informal and formal, micro and large, domestic and foreign companies are very weak, further limiting companies’ potential to expand, diversify, innovate and build up skills. Limited focus on value addition of raw materials and commodities remain a major stumbling block as well as the access to markets.

Unemployment and poverty remains a major challenge in Kenya today. Kenya’s steady economic growth has not effectively translated into more job creation and poverty reduction, and economic inequality in the country remains the highest in the East African region. The poor and vulnerable, especially women and youth, do not sufficiently participate in, benefit from and shape economic growth. The relatively high unemployment rate among the youth in Kenya is attributed to a rapidly growing youth population, the inability of the economy to create a sufficient number of good quality jobs, relatively low levels of education attainment, lack of appropriate labour market skills, insecurity of employment in formal sector and seasonal fluctuations in labour demand, job selectiveness, and information asymmetries in the labour market, among others.

The youth in arid and semi-arid areas are more vulnerable and suffer greater share of the challenges of unemployment, lack of access to education, skills and training, and lack of business development support and opportunities. Another challenge is that the majority of the youth does not have appropriate academic and technical skills. Youth unemployment in Kenya is therefore both an outcome of limited employment opportunities and lack of employable skills, which is compounded by the mismatch between skills and the demands of the labour market. The high unemployment and inactivity among the youth also impacts negatively on social cohesion and integration due to increased crime rates and proliferation of criminal gangs/militia groups.

Several initiatives and programmes have been implemented in the past targeting the weaknesses of the MSME sector, but with insufficient impacts. There is a need for a well-coordinated, demand-driven and needs based response for the needs of Kenya’s micro and small enterprises at the county level.  Towards this direction, the Government of Kenya and its development partners have identified, through the second Medium Term Plan (MTP II) for 2013-2017, the need to focus on:

(i)	Promoting growth and development of SMEs in order to enhance employment creation and poverty reduction, and

(ii)	Moving towards a formalized domestic trade sector that is efficient, multi-tiered, and diversified in product range and innovation.

In this regard, the county governments will be expected to play a key role in promoting sustainable economic growth and job creation.

1.2	The Economic Empowerment Programme

In response to the challenges outlined in paragraph 1.1 above, amongst others, a 4 year (July 2014- June 2018) Economic Empowerment Programme (EEP) was developed to contribute to reducing these challenges by empowering the citizenry in different ways focusing on national priorities contained in Kenya’s Vision 2030 Economic Pillar, UNDAF 2014-2018 and UNDP Kenya CPD 2014-2018.

The overall outcomes are stated as:

(i) 	promote a business environment conducive for MSE sector development and the economic inclusion of youth/women, and public-private collaboration; and

(ii)	empower poor and vulnerable (in particular women/youth) as economic agents.

The programme outputs include:

(i) 	Capacity of public and private institutions at national/county level strengthened to promote SME-driven private sector development;

(ii)	National, county and private sector actors enabled to establish partnerships, create inclusive economic opportunities and transform productive capacities for sustainable job creation;

(iii)	One stop County Business Development (CBD) centres established and strengthened to enhance service delivery;

(iv)	Youth and women accessing market driven vocational and entrepreneurial skills increased and are employable and National Occupations Frameworks in place.

The specific objectives of the programme are to:

(i)	support development and implementation of policies;

(ii)	strengthen capacities of public-private sector institutions;

(iii)	support establishment and operationalization CBD centres;

(iv)	facilitate review, development and or implementation of educational, vocational, technical and industrial related frameworks, curriculum and support materials;

(v)	Strengthen capacities of BDS providers; and

(vi)	facilitate development of viable business models and value chains.

The programme deliverables are categorized into two, namely:

(i)	National/upstream deliverables focusing on private sector development, policy, and strategies; and

(ii)	County/downstream deliverables focusing on operationalization and support to MSEs, youth, women, the poor and disadvantaged including people living with HIV/Aids.

The programme consists of the following three components:

i.	Programme Component I: Inclusive Growth (Upstream): Business environment for micro and small enterprises (MSEs) sector development improved; the economic inclusion of youth and women ensured; and public-private sector collaboration is enhanced.

ii.	Programme Component II: Economic Empowerment of Women and Youth (Downstream):  The poor and vulnerable (in particular women and youth) are empowered as economic agents with strengthened capabilities and opportunities to engage in, benefit from and shape the market systems they are interacting in.

iii.	Programme Component III:  Programme Coordination:  Coordination mechanisms for project implementation operationalized and strengthened.  This incorporates inputs which includes project personnel, training, advocacy, equipment, contractual services, logistics, management teams amongst others.

1.3	Programme Management arrangements

The key stakeholders include the Ministry of Devolution is the Implementing partner, UNDP and the following Responsible Parties or Partners:  Ministry of Agriculture, Livestock and Fisheries; Ministry of Education, Science and Technology; Ministry of Industry, Trade and Cooperatives, Micro and Small Enterprise Authority (MSEA); National Industrial Training Authority (NITA); Kenya Investment Authority (KENIVEST); Kenya National Chamber of Commerce and Industry (KNCCI); Kenya Private Sector Alliance (KEPSA), Youth Enterprise Development Fund (YEDF); Housing Finance Foundation (HFF); Kenya Association of Manufacturers (KAM); and County Governments (various).  The programme management arrangements is highlighted in the organization structure shown below.

1.4	Purpose of the Assignment

The purpose of this assignment was to undertake a mid-term review which would examine the performance of the Economic Empowerment Programme.  In this regard the review:

1.	provides an overall assessment of progress and achievements made against planned results as well as assess and document challenges and lessons learnt during implementation.

2.	focuses on changes around the programmatic environment which has affected EEP programming or impacted on implementation of the EEP and realization of programme results.

3.	reflects on how the UNDP has supported the Government of Kenya Development Agenda especially Medium Term Plan II (MTP II) and Vision 2030.

4.	identifies areas requiring additional support either in programme management or new implementation strategies including exploring the possibilities of new partnerships.

5.	reflects on the EEP theory of change and reflects on its continued relevance to the remaining programming cycle. Key issues of concern include the reflection on how gender has been incorporated in the programming, the sustainability of results, etc.

6.	reflects on the programme alignment to the UNDP strategic plan with recommendations for the same.

The review more specifically includes:

1.	Assessment of the progress in implementation measured against planned outputs set forth in the Programme Document in accordance with availed/allocated budget and the assessment of features related to the process involved in achieving those outputs as well as the initial and potential impacts of the Programme.

2.	Identification of and highlighting issues and challenges contributing to targets not adequately achieved within the mid-term period; and make recommendations.

3.	identification and documentation of Programme successes, opportunities for improvement, weaknesses and strengths of the programme design with recommendations for any necessary changes in the overall design and assessing the adequacy, efficiency, and effectiveness of its implementation, as well as assessing the programme outputs and outcomes to date.

4.	Detailed recommendations on the work plan for the remaining programme period including assessment of early signs of the programme success or failure and prompt necessary adjustments.

5.	Identification of lessons learnt and best practices which could be applied to other related on-going and future interventions.

1.5	Review Methodology:

The MTR team which consisted of Lead Consultant and Assistant Consultant) enlisted the full participation of the Manager/Director - Social Governance, Ministry of Devolution and Planning and the Officer In charge - Inclusive Economic Growth Unit (UNDP). The consultants interviewed top policy makers in the Ministry of Devolution and Planning, Ministry of Education, Science & Technology and other relevant government departments, development partners as well as key stakeholders from the private sector and civil society.  The consultants, who visited the county of Kwale and Turkana, held meetings with key opinion leaders, representatives of beneficiaries, prospective intermediaries and other relevant target groups in the counties of Kwale, Taita Taveta, Marsabit and Turkana where Biashara Centres have been established.

A variety of data collection methods were used including desk review of relevant documents. The assessment used the following three approaches to collect data:

1.	The first method was assessment on performance of planned outputs and outcomes to determine performance of outcomes and outputs based on an analysis of available evidence as presented by the stakeholders

2.  	The second method assessed performance of outcome indicators in the Programme Document by reviewing data contained in progress reports.

3.	The third method was independent opinion of the MTR team informed by assessment of available data, documents review, informant interviews and questionnaires (Annex 3).

A total of 67 persons were reached through one-on-one interviews and focused group discussions while 40 beneficiaries and intermediaries were reached through questionnaires. Another 40 stakeholders are expected to be reached through Stakeholder Validation Workshop.

1.6	Limitations of the Review

The MTR team experienced the following major limitations in carrying out the assignment:

1.	The timing of the review came at a time when many of the partners were busy trying to complete end of year activities before breaking off for Christmas festivities.  December is also a month when many employees take early leave. Consequently, it was difficult to make interview appointments with many partners and stakeholders both in public and private sector, civil society stakeholders. It was equally difficulties in some areas to contact beneficiaries for one-on-one interviews or administer questionnaires.  The MTR team however managed to interview a representative sample of the respondents as indicated in Annex 3.

2.	There was lack of proper documentation as well as a comprehensive and user friendly data base on programme activities and especially at the counties. This resulted in delays in obtaining data, including financial reports which are essential in tracking progress and resource utilization.

3.	Retrieval of project documents and other related data was partly slow due to the fact that the office of the Project Coordinator, Project Officer and GOK counterpart at Bruce House have not been operational for a whole year.

However, the Inclusive Economic Growth Unit at UNDP availed most of the documents and data as well as logistic support required for the review, hence mitigating some of the impact of the above limitations.

2.0	REVIEW OF ACHIEVEMENTS AND KEY ISSUES

During the interviews and discussions with stakeholders, the MTR team noted that the Programme enjoyed strong good-will from the Government, UNDP and other partners. They particularly acknowledged the ability of the Implementing Partner and UNDP to provide the required resources and organize stakeholder forums and meetings that brings together various partners.

2.1	Key Findings

Output 1.1	Capacity of public and private institutions at national and county level

strengthened to promote MSME-driven private sector development through promotion of

local capacities & innovations

Through EEP, Technical, and managerial capacities of key national and county institutions involved in a number of activities such as County Biashara (Business) Centres, National Industrial Training Authority (NITA), Department of Vocational Education Training (DVET) -YP/VTCs Strategy, Micro and Small Enterprise Authority (MSEA)- MSEA Strategic plan 2013-2017, Youth Enterprise Development Fund (YEDF) - Youth Entrepreneurship Strategy and the Kenya National Chamber of Commerce and Industry (KNCCI) have been enhanced to support MSMEs. The institutional capacity assessment for KNCCI has led to re-organization of KNCCI and also supported formulation of a Strategic Plan for KNCCI, now guiding operations of the institution. The youth have also been supported through development of the National Youth Employment Strategy.

EEP has also endeavoured to partner with other institutions to come up with policies that encourage participation of the MSME. One such partnership is with the Poverty Eradication Commission whereby they partnered to conduct a study on Mainstreaming Equity and Poverty Reduction in Government policies and programmes.

Output 1.2 	National, county & private sector actors enabled to establish partnerships, create inclusive economic opportunities and transform productive capacities for sustainable job creation and improved livelihoods

The YEF has partnered with the four county Biashara centres in training their beneficiaries.  In 2015, EEP facilitated YEF to train 60 start-ups out of whom 46 received start-up funds.  The YEF also collaborated with EEP during the International Youth Day where over 4,000 participated.

At the county level there are a number of institutions that have partnered to ensure that local capacity and innovations are encouraged through Financial Institutions like KCB Bank Kenya Limited, Non-Governmental Organizations likes International Organization for Migration (IOM).

In Kwale county EEP has not only partnered with the county but also financial institutions that are willing to provide finances to women and youth groups in certain value chains. LungaLunga Livestock and Kidzo Dairy are some of the groups that have benefitted from value chain financing project. This has enabled the farmers to buy more livestock, created employment and improved their livelihoods through profitable sales that have been realized.

Output 2.1	One stop County Biashara centres established and strengthened to enhance service delivery for MSMEs in counties

The Biashara Centres established at county level are improving service delivery and enhancing capacity for business management and business start-up. In partnership with the county governments and the private sector, the UN has provided both technical and financial support for establishment of office facilities including ICT laboratories with modern equipment and operationalization of the centres in 4 counties, Kwale, Marsabit, Turkana and Taita Taveta.  Some of the centres got short term technical support in form of UN Volunteers to provide expertise to the county governments in coordination and increasing outreach and access to business development services. Other than the UNVs, each of the BCs was provided with an EDA being experts in operationalization of the centres for a period of 6 months.

Some of the benefits from BCs include, formal registration of businesses which brings many benefits, such as better access to services and institutions (such as courts), lower burden from inspections and other government officials, as well as limited liability of the owner vis-a-vis the firm. In partnership with the Ministry of Devolution and Planning, Ministry of Public Service, Youth and Gender Affairs; County Governments and Youth Enterprise Development Fund, a total of 767 youth have been capacitated to access the 30% government procurement opportunities through the Access to Government Procurement Opportunities (AGPO) training in partnership with the Ministry of Devolution and Planning

Output 2.2	Youth & Women accessing market driven vocational/entrepreneurial skills increased and are employable and National Occupations Frameworks in place

EEP facilitated finalization of National Occupational Qualification Framework and the development of National Competency Standards and Progression Pathways in collaboration with the private sector for 5 trade areas ensuring alignment with and responsiveness to industry focus. The Programme also supported in VTCs through training in governance and management as well as revision of curriculum for 4 trade areas which are responsive to market demands and needs. The youth have also benefited from awareness creation on Public Procurement and Disposal Act 2015 including training on Access to Government Procurement Opportunities (AGPO).

Output 3.0	Coordination mechanisms for project implementation operationalized and strengthened

Project Coordination office in Bruce House 8th Floor established and Project Coordinator employed but contract ended in December 2015. Salaries for UNVs and BDS officers at  Kwale and Taita Taveta BCs paid by the project.

2.2	Key issues that have hindered achievements

1.	Some Responsible Partners complained of operated in isolation with limited interaction forum for sharing of strategies and experiences. It was also noted that a number of Responsible Partners did not attend Technical Committee meetings while others such as Ministry of Industry, Trade and Cooperatives and Kenya Association of Manufacturers (KAM) do not appear to have been active in implementing programme activities. Information dissemination about the programme activities among partners was lacking.

2.	A number of responsible partners such as MoEST, NITA, MoALF, Biashara centres and the Poverty Eradication Commission complained of delayed or inadequate funding of programme activities. The was no evidence of a formal agreement between the Implementing Partner and the Responsible Partners as stipulated in paragraph 4.2.8 of PRODOC; hence it was difficult to verify the complaints regarding funding.

3.	For some technical reasons, such as lack of 3-phase power supply, the ICT laboratories at the Biashara centres are idle and something needs to be done to make them operational.

4.	The contract for the Project Coordinator expired in December 2015 and the position has been vacant since then. Also vacant is the position of the Project Officer (UNV). The MTR team noted that the vacancies have created a major gap in the implementation considering the role expected to be played by the Project Coordinator as stipulated in paragraphs 4.2 and 4.2.10 of the PRODOC.

5.	The EEP does not seem to adequately address aspects of innovation and incubation of innovative ideas. These are initiatives which require heavy capital investments and a long duration before one realizes desired results.

3.0	WEAKNESSES AND STRENGTHS OF PROGRAMME DESIGN

3.1	(a) Project Strategy/Project design

The Economic Empowerment Programme is a very ambitious programme trying to achieve too much within a limited time frame and resources.  There is need to review the activities for the remaining period and focus on few interventions which can have a long-term impact and  achieved within the remaining one and half years.

The PRODOC, paragraph 4.2 clearly states that “In order to support implementation of project activities and relatively relieve the Implementing Partner (IP) of the administrative and logistical issues, a Project Management and Coordination Unit has been established. This Unit is accountable to the IP. Paragraph 4.2.10 further states that the Project Support role shall provide project administration, management, project documentation management, financial management, monitoring and reporting and technical support services to the National Project Manager as required by the needs of this project.

While the PRODOC has three outcomes it contains four very heavily loaded outputs which have not conformed to the basic SMART principle. Three of these outputs are lengthy and sometimes difficult to comprehend fully. At least three outputs could have been derived from Outcome no.1.and three other outputs from Outcome no.2.

On the other hand, the PRODOC does not indicate how many Biashara Centres were to be established. Documents used during the inception phase which ended in June 2014 including January to September 2016 Progress Report indicate that 20 centres were targeted but now only four Biashara Centres have been established.  In this regard, it is important to rationalize the establishment of the one stop investment centre as a stand along facility or incorporate such a centre within the Biashara Centres where they exist.

The 2014/2015 and 2016/2017 Work Plans seems to have adequately targeted inclusion of Exit Strategy and institutionalization activities although this was done partly by the BDS experts who operationalized the BCs.

3.1 	(b) Results Framework/Log frame

The MTR team reviewed the annual work plans for 2014/2015 and 2016/2017 as well as quarterly work plans for July to September 2015 and April to June 2016.  The 2015/2016 annual work plan and quarterly work plans for the other periods between 2014 and 2015 were not available. Although the quarterly work plans contained specific activities all the work plans which were reviewed lacked clear targets and verifiable indicators.

3.2	Progress towards Results- Progress towards Outcomes Analysis

Some of the progress reports were done on quarterly basis while others were for three quarters and in different formats but no Annual Project Review Reports as is required in the PRODOC.   Nevertheless, the MTR team noted good progress in a number of project outputs has indicated below.

For project output 1.1, Technical, and managerial capacities of key national and county institutions involved in has been enhanced. Support has also been provided to:  YEDF; NITA; KNCCI; MSEA to develop a Strategic Plan 3013-2017 plus an MSE Coordination and Harmonization Framework for Counties; KenInvest in the process of developing a National Investment Policy; Development of the National Youth Empowerment Strategy; and Finalization of the YP/VTCs Strategy through DTVET.

For project output 1.2, support had been provided to: Carry out AGPO training in Marsabit, Turkana, Kwale, Taita Taveta and Nakuru counties for over 2,000 youth; BCtA with KEPSA had organized a consultative forum with the private sector to make commitments for youth employment; and organised joint event and launched report with PSP4H on Health Sector – Use of technology / mobile platforms to increase access to health care in Kenya.

For project output 2.1, four Biashara Centres have been established (Taita Taveta, Kwale, Marsabit, Turkana) out of the planned 20.

For project output 2.2, support has been provided to: NITA to develop the National Occupational Qualification Framework and competency standards and progression pathways for 5 sectors awaiting printing; Taita Taveta Biashara Centre to train thirty (30) youths in BS&ED; Kwale Biashara Centre to train thirty-six (36, 14 female) youths in BS&ED; AFIM / ASDP project to distribute new technology water barrels to women in rural communities – Turkana (300), Marsabit (150); and Kwale and Taita Taveta counties to undertake a quick feasibility study for agro-value chains.

For Project Output 3.0 established Project Coordination office in Bruce House with Floor and Employed a Project Coordinator whose contract ended in December 2015 and paying salaries for Biashara Centre staff in Kwale and Taita Taveta.

The MTR team noted that a number of activities planned for 2014 were pushed to 2015.  It was also noted that a number of activities are pending completion due to financial constraints.  Overall, the programme implementation is on track subject to some adjustments on critical interventions that will be required for the 2017/2018 period.

3.3	Performance Review

Relevance

The Economic Empowerment Programme (EEP) is relevant in that it seeks to contribute to reducing socio-economic challenges by empowering the citizenry in different ways focusing on national county government priorities contained in Kenya’s Vision 2030 Economic Pillar and MTP II, UNDAF 2014-2018 and UNDP Kenya CPD 2014-2018. It is quite encouraging to note that some of the EEP initiatives are also being incorporated by county governments the BCs in the County Integrated Development Plans (CIDPs).

Effectiveness

EEP has registered significant results in development of policies and strategies to support the drive towards a prosperous society that is characteristic of skilled people, safe employment opportunities and the ease of doing business. Key promising results include: (i). Biashara Centres established at county levels are providing breakthroughs for service delivery and enhanced capacity on business management and business start-ups; (ii) Encouragement of youth in to engage in agribusiness value chains is going to transform their lives; (iii) The EEP partners have supported development of supportive policies and strategies for job creation, skills development and working conditions; (iv). Significant progress has been made to promote professional experiences and skills of young people for the labour market through internship programs for the youth; (v) Good progress has been registered in efforts towards creation of a One Stop Investment Centre (OSIC) for investors; and (vi) Strong partnerships between the GOK and UN have led to sustained investment in expanding economic opportunities for women-owned enterprises in the public procurement sector both at national and county levels. However, the government policy to award at least 30% of all procurement opportunities to the youth, women and people with disabilities has not been fully exploited.

The Biashara Centre concept has adopted an area-based programming approach that has enabled the UN to provide targeted technical, financial and institutional support in a coordinated manner to Turkana and Marsabit counties. The planning processes have been highly participatory through consultations with the communities, county governments and UN. The GOK and UN have generated evidence-based information for programming.

Efficiency

The EEP PRODOC has put in place thorough structures, policies and procedures that ensure programmatic efficiency: At the Apex, the EEP is coordinated by the Project Board/National Steering Committee chaired by the Principal Secretary, Devolution and Planning supported by the UNDP ACD/Head of Program a.i. The EEP Technical Committee coordinates and monitors implementation of Annual Work Plans (AWPs) based on approved budgets. Under the current arrangements, project funding is being used as agreed but delays are being experienced in refunding partners for costs incurred.

The current Technical Committee is functional but can be strengthened for comprehensiveness, smarter results and stronger linkages. Standard Project logical frameworks should be prepared to incorporating SMART objectives, performance indicators and targets which will equally raise the qualitative and quantitative aspects of the progress reports.

The long absence of a Project Coordinator and support team has seriously affected the efficiency in the implementation of the programme.

Sustainability and Impact

The MTR team has noted that there is evidence indicating a high degree of potential for continuity of Programme benefits. EEP interventions are in high demand to support the devolution process. For sustainability, running costs at BCs are catered for by the County Governments.

Network /linkages

Twelve institutions including 3 government Ministries, 3 state corporations, 5 private sector players and 4 county governments are participating in the implementation of the Economic Empowerment Programme. Most of the twelve institutions focus on youth and women target groups. There is need to increase players from the private sector and civil society organizations.

The strategy for working with Private Sector focuses on four areas I) resource transfer, ii) technology transfer; iii) facilitating or brokering innovative private investments, and iv) value chain linkages of “inclusive business” approaches. Also, some CSOs, in Kenya are now keen to collaborate with the GOK and the UN to enhance their legitimacy to development efforts.

While EEP has done an excellent job in producing communication and publicity materials Biashara Centres, the outreach needs to be expanded.

4.0	KEY RECOMMENDATIONS

1. 	The current outputs should be redefined with a view of reducing them into a few interventions which can have a long-term impact and can be achieved within the remaining one and half years more specifically 1.1.1(b), 1.2.1(g), 2.1.1, 2.2.2 (b) and 2.2.3 (d).

2.	In order to benefit from the gains made through EEP so far, it is advisable for the IP to take the lead to provide a Project Coordinator who will perform the role spelt out in paragraph 4.2.10 of the PRODOC with an office preferably at the Ministry of Devolution and Planning.

3.	A forum should be created for Responsible Partners whose contribution is still relevant in the implementation of the remaining programme activities once in a quarter to review achievements and prepare quarterly work plan for the next quarter.  Where a Responsible Partner is engaged to implement some project activities, formal agreements should be made between the Implementing Partner and the Responsible Partners as stipulated in paragraph 4.2.8 of PRODOC.

4.	The Project Board should review the strategy of establishing county Biashara Centres and the one stop investment centres considering the high initial capital for providing the infrastructure and competent personnel.

5.	As part of an exit strategy and sustainability it is important for the Implementing Partner to initiate institutionalization strategies guided by MOUs with county governments for purposes of setting a uniform approach of ownership and leadership.

6.	For the period 2017 to 2018, quarterly work plans should be prepared following the standard project logical framework which includes clearly indicates: (1) objectively verifiable indicators of achievement; (2) sources and means of verification; and (3) assumptions.

7.	There is also need for the project to broaden the knowledge management products including establishing a comprehensive documentation management system which will make it easy to disseminate information partners and general public.

5.0	LESSONS LEARNT AND BEST PRACTICES

1.	The first half of EEP implementation has generated knowledge and new partnerships, which offer opportunities for upscaling, replication and adjustments for positive future.

2.	So far, EEP has been relying on TRAC funds from UNDP, with minimal support in form of running costs and from the respective County Governments.  The contribution in cost sharing needs to be clearly stated at the project design at national and county government levels based on best practices in some developing countries.

6.0	REFERENCES

7.0	ANNEXES

7.3: ANNEX 3: INTERVIEWS AND VISITS ITINERARY

| NAIROBI |
| --- |
| Name | Particulars | Contact | Date |
| 1. PATRICK MAINGI | PROGRAMME OFFICER, IEG,UNDP | 0727680344 | 25 November 2016 |
| 2. BONIFACE KITILI | TEAM LEADER, IEG, UNDP | 0720639407 | 01 December 2016 |
| 3. HENRY GAKIO MWAURA | GoK PROGRAMME COUNTERPART | 0725514364 | 01 December 2016 |
| 4. CHRISANTOS OKIOMA | MODP, SOCIAL & GOVERNANCE DIRECTORATE | 0725615744 | 05 December 2016 |
| 5. DOUGLAS MANYARA | MODP, SOCIAL & GOVERNANCE DIRECTORATE | 0729933777 | 07 December 2016 |
| 8. MORRIS ONDIEK | YOUTH ENTERPRISE DEVELOPMENT FUND | 0701101482 | 06 December 2016 |
| 7. JOSEPHINE KASERA | TIVET AUTHORITY, MINISTRY OF EDUCATION, SCIENCE & TECHNOLOGY | 0720023803 | 06 December 2016 |
| 8. LEONARD OBIDHA | POVERTY ERADICATION COMMISSION | 0720215932 | 06 December 2016 |
| 9. CAROLINE SIKASA | DIRECTOR, HOUSING FINANCE FOUNDATION CENTRE | 020 3262000 | 14 December 2016 |
| 10.MUNYASIA HENRY SIMIYU | NITA | 0723336067 | 15 December 2016 |
| 11. WYCLIFFE OTIENO | NITA | 0712817902 | 15 December 2016 |
| 12. MATENDA WEBUYELE | KNCCI | 0722202939 0722522924 | 17 December 2016 |
| TURKANA |
| 1. JAMES LOKWALE | DIRECTOR OF TRADE AND INDUSTRILIZATION, TURKANA COUNTY | 0729742058 | 07 December 2016 |
| 2. MIKE NDETO MUSYOKI | AG. CENTRE MANAGER AND TRADE DEVELOPMENT OFFICER, TURKANA CENTRAL SUB-COUNTY | 0713258565 | 07 December 2016 |
| 3. DAMARIS KAMAU | TRADE DEVELOPMENT OFFICER, TURKANA NORTH | 0722882683 | 07 December 2016 |
| 4. PURITY NATAMBO | TRADE DEVELOPMENT OFFICER, TURKANA SOUTH | 0701264042 | 07 December 2016 |
| 5.KEVIN EMERI | ENTERPRISE DEVELOPMENT OFFICER | 0706472858 | 07 December 2016 |
| 6. JOHN EBEI | SUPPLIER OF BODA BODA SPARE PARTS AND GRADUATE OF ENTERPRISE DEVELOPMENTAND BUSINESS SKILLS TRAINING BETWEEN 19-29 JULY 2016 | 0718104293 | 08 December 2016 |
| 7. ISAAC LOCHILIA | BARBER AND GRADUATE OF ENTERPRISE DEVELOPMENTAND BUSINESS SKILLS TRAINING BETWEEN 19-29 JULY 2016 | 0724710557 | 08 December 2016 |
| 8. KHADIJA KAMZEE | CHAIRPERSON, TWAP BASKETERY WOMEN GROUP, KANAMKEMER | 0729268631 | 08 December 2016 |
| 9. PAULINE NAPIO | SECRETARY, TWAP BASKETERY WOMEN GROUP, KANAMKEMER | 0726069862 | 08 December 2016 |
| 10. TRUPHENA ANAM | MEMBER, TWAP BASKETERY WOMEN GROUP, KANAMKEMER | 0729640707 | 08 December 2016 |
| KWALE |
| 1. EMILY OSENA | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | 0726812883 | 07 December 2016 |
| 2. JOYCE KADZE | UNITED NATIONS VOLUNTEER | 0720011999 | 07 December 2016 |
| 3. JOSEPH KESI | SECRETARY LUNGA LUNGA LIVESTOCK TRADERS | 0717251235 | 08 December , 2016 |
| 4. DAVID MAUNDU | CHAIRPERSON LUNGA LUNGA LIVESTOCK TRADERS | 0718669398 | 08 December 2016 |
| 5. SHEE YUSUF | VICE CHAIR PERSON JIMBO FISHERMEN | 0729679621 | 08 December 2016 |
| 6. ALI SHILLINGI | CHAIRMAN JIMBO FISHERMEN | 0719337573 | 08 December 2016 |
| 7. JOEL MWITI | BENEFICIARY- BASIC ENTREPRENEURSHIP PROGRAM | 0713498197 | 08 December 2016 |
| 8. JOSEPH ODEKA | BENEFICIARY- BASIC ENTREPRENEURSHIP PROGRAM | 0728921176 | 08 December 2016 |
| 9. HELEN NAKHATAMA JUMA | BENEFICIARY- BASIC ENTREPRENEURSHIP PROGRAM | 0712012053 | 08 December 2016 |
| TAITA TAVETA |
| 1. RICHARD WANDANA KIBENGO | DIRECTOR OF TRADE AND COMMUNITY AFFAIRS | 0726602525 | 14 December 2016 |
| 2. ROBERT MWASHASHU | PROJECT OFFICER, TAITA TAVEA BIASHARA CENTRE | 0723071000 0734997824 | 14 December 2016 |
| MARSABIT |
| 1. PETER LERUK | DIRECTOR OF INDUSTRIAL AND TRADE DEVELOPMENT | 0722622742 | 14 December 2016 |

# Text boxes

Project Board

PS – The Treasury

IP – Project Manager

Ministry of Devolution & Planning

(UNDP Programme Manager)

(RR)/ Development Partners

IP National Project Manager

(IP Project Manager)

Ministry of Devolution & Planning

Project Support

Project Coordinator (1)

Project Officer –UNV (1)

GOK Project Support Team

Project Assurance

(Programme Officer – UNDP)

RESPONSIBLE PARTIES

Project Organization Structure