## Slide 1: UNDP Lebanon COUNTRY PROGRAMME DOCUMENT 2017 Annual Review
30 October 2017

## Slide 2: Country Programme Document 2017-2020
2. (UNSF 2.1): Government's ability to improve the performance of institutions and promote participation and accountability Increased – SP 2
1.1 Evidence-based peaceful dialogue on key national issues institutionalized at all levels
2.1 Capacity for inclusive and credible elections increased
2.3 Government institutions core state functions and capacities strengthened for accountability and policy formulation and reform enhanced
CPD OUTCOMES
KEY OUTPUTS
1.2 Systems and capacities in place to monitor tensions and maintain peace
3. (UNSF 3.1) Productive sectors strengthened to promote inclusive growth and local development especially in most disadvantaged areas– SP 6
3.1 Livelihood and economic opportunities increased (especially for women and youth)
3.2 Improved capacity of national and local Institutions to respond to local needs in an integrated and coordinated way
4.1 Low emission climate resilient actions initiated
4. (UNSF 3.3) Lebanon has adopted measures to improve environmental Governance - SP 1
(UNSF 1.3): Lebanon has institutionalized mechanisms to promote peace and prevent, mitigate and manage conflict at national, municipal and community levels – SP 5
4.2 National Environmental Management Strengthened
1.3 Systems and capacities in place to govern municipal police roles
2.2 Inclusive and participatory policies and decision making processes enhanced

## Slide 3
2. Government's ability to improve the performance of institutions and promote participation and accountability Increased
CPD Outcomes
3. Productive sectors strengthened to promote inclusive growth and local development especially in most disadvantaged areas
4. Lebanon has adopted measures to improve environmental Governance
Lebanon has institutionalized mechanisms to promote peace and prevent, mitigate and manage conflict at national, municipal and community levels

## Slide 4
Progress and main achievements in 2017
Lebanon has institutionalized mechanisms to promote peace and prevent, mitigate and manage conflict at national, municipal and community levels
A national political dialogue unified roadmap pertaining to Palestinian refugees affairs
Political Parties’ dialogue on response to the Syrian refugees crisis producing a position paper.
Conducted a the first ever Palestinian Refugees Population and Housing Census in Camps and Gatherings evidence based policy development
Host communities & refugees have access to basic security service strengthening of Municipal Police (including women promotion)
MOIM has a strengthened early warning mechanism monitoring community tensions
Prison detention conditions improved including support to upholding HR (Roumieh central prison)
LMAC abiding by CCM obligations strategy review conducted
National Mine Action Standards updated and in line with International ones speeding up clearance operations
Mine Action including MRE in Lebanon is now all inclusive refugee communities
Output 1 Evidence-based peaceful dialogue on key national issues institutionalized at all levels.
Baseline: 5
Target: 15
Output 2 Systems and capacities in place to monitor tensions and maintain peace.
Baseline: 50
Target: 212
Output 3 Systems and capacities in place to govern municipal police roles.
Baseline: 0
Target: 200
92
18
30

## Slide 5
Expected results 2018
Lebanon has institutionalized mechanisms to promote peace and prevent, mitigate and manage conflict at national, municipal and community levels
Municipal Police standard operating procedures and code of conduct to be endorsed by MOIM (adopted by pilot municipalities - 30)
Locally led peace building mechanisms developed within host communities contributing to mitigating communal conflicts (up to 38) , with MOSA SDCs taking lead in facilitating such processes
Palestinian census results made available to inform the Government of Lebanon policy regarding Palestinian refugees adopted by Government of Lebanon (e.g. employment, NSF)
Technical assistance provided to ensure that the LMAC regional humanitarian demining school is operational and caters to Lebanon and neighboring countries’ needs
Joint LMAC – Private sector coalition put in place and mechanisms establish to support sustained financing of this sector.

## Slide 6
2. Government's ability to improve the performance of institutions and promote participation and accountability Increased
Progress and main achievements in 2017
Output 2.1 Increased capacity for inclusive and credible elections
Indicator 2.1.1. No. of legal electoral reforms introduced consistent with international standards
Baseline: 0
Target: 1
Indicator 2.1.2. No. of measures adopted to increase women’s representation
Baseline: 0
Target: 2
Technical contribution provided to the new electoral law passed in Parliament, based on the introduction of new reforms (PR voting system and unified ballot).
Technical support to MOIM and other stakeholders (e.g. women’s organizations) initiated in preparation for the 2018 parliamentary elections.

## Slide 7
2. Government's ability to improve the performance of institutions and promote participation and accountability Increased
Progress and main achievements in 2017
Output 2.2 Inclusive and participatory policies and decision making processes enhanced
Indicator 2.2.1. No. of consultative sessions held between parliamentary committees and civil society and private sector, particularly women and youth organizations
Baseline: 0
Target: 10
4 consultation with CSOs undertaken at the Lebanese parliament and key legislative reforms introduced and/or discussed (e.g. access to information, child marriage, women political participation, and human rights).
Guidelines to integrate SDGs in parliamentary oversight introduced.
2 Hearing sessions organized to address development needs and challenges in Akkar and Nabatieh.

## Slide 8
2. Government's ability to improve the performance of institutions and promote participation and accountability Increased
Progress and main achievements in 2017
Output 2.3. Government institutions core state functions and capacities strengthened for accountability and enhanced policy formulation and reform
Policy advice and coordination for social, economic and fiscal policies in place at the PCM.
Technical assistance provided to the GoL in the formulation of key strategies and plans, particularly in relation to: anti-corruption, disaster risk management and gender equality.
Support to administrative reform supported in key public institutions, including strategic planning, KPIs, and digital transformation.
Indicator 2.3.3. No. of draft justice reforms laws prepared and submitted to parliament
Baseline: 0
Target: 5
Indicator 2.3.4. Completion of Sustainable Development Goal progress report
Baseline: 0
Target: 2
Indicator 2.3.2. No. of approved administrative reform initiatives implemented
Baseline: 0
Target: 5
Indicator 2.3.1. No. of draft laws relevant to administrative and fiscal reforms prepared and submitted to parliament
Baseline: 38
Target: 150

## Slide 9
2. Government's ability to improve the performance of institutions and promote participation and accountability Increased
Expected results 2018
Support provided to the Ministry of Interior and Municipalities for free and fair, parliamentary elections;
Technical assistance in place to support the establishment and functionality of the Supervisory Commission on Elections;
Public policy coordination in place at the OPCM, with a focus on new key areas of governance (e.g. oil and gas, entrepreneurship, transportation and PVE).
Administrative reform initiatives under the leadership of OMSAE, in particular related to digital transformation, scaled up.

## Slide 10
Progress and main achievements in 2017
3. Productive sectors strengthened to promote inclusive growth and local development especially in most disadvantaged areas
Output 3.1. Livelihood and economic opportunities increased
Indicator 3.1.1. No. of income generating initiatives supported
Baseline: 24
Target: 100
Indicator 3.1.2. No. of supported SMEs with sustainable operations after 1 year
Baseline: 20
Target 90
Indicator 3.1.3. No. of value-chain developed for small producer groups
Baseline: 0
Target: 3
  40 income generation initiatives were supported across a range of interventions related to youth employability, SMEs/cooperatives support, and economic Infrastructure.
  167 MSMEs/Cooperatives were supported through technical and in-kind support.
  6 value chain assessments were initiated: 3 in agriculture (Freekeh, Oregano and Honey) and 3 in renewable energy.

## Slide 11
Output 3.1. Livelihood and economic opportunities increased
Indicator 3.1.4. Business and employment support institutions strengthened
Baseline: 0
Target: 3 institutions
Indicator 3.1.5. Joint initiatives with target enterprises
Baseline: 0
Target: 5 initiatives
Progress and achievements in 2017
3. Productive sectors strengthened to promote inclusive growth and local development especially in most disadvantaged areas
  5 partners involved in business and employment support (Chambers of Commerce, Business Incubators) were engaged in the youth employability project.
  One vocational training center was supported through rehabilitation and provision of equipment.
  Two joint initiatives were implemented with the private sector targeting 20 women cooperatives to improve their market outreach (Cascada Mall and Nature).

## Slide 12
12
Output 3.2. Improved capacity of national and local Institutions to respond to local needs in an integrated and coordinated way
Indicator 3.2.1. No. of multi-sectoral local and sub-national plans adopted
Baseline: 95
Target: 200
Indicator 3.2.2. Participation of men and women in local development planning
Baseline: 1,425 (men: 1,100; women: 325)
Target: 3,000 (men: 2,000; Women: 1,000)
Indicator 3.2.3. No. of improved infrastructure and quality basic services initiatives completed
Baseline: 92
Target: 450
Indicator 3.2.4. Completion of multi-dimensional poverty assessment
Baseline: 0
Target: 1
3. Productive sectors strengthened to promote inclusive growth and local development especially in most disadvantaged areas
Progress and achievements in 2017
14 multi-sectoral sub-national plans (cluster level MRRs) were developed and 206 multi-sectoral local plans (community level MRRs) were updated.
635 participants (536 men and 99 women) were involved in the development of the cluster plans; 5496 participants (3941 Males 1555 Females) were involved in the communities plans.
27 projects in Basic Services were completed benefitting 31 vulnerable communities in response to the Syrian crisis and 42 projects were implemented in the Palestinian Gatherings.
A rapid poverty assessment undertaken with the Ministry of Social Affairs was finalized.
Notes: CEDRO: 3 videos, army report, wind grid code
DREG: Solar grid code, DREI, PV training
CC: 2 NAMAs, Paris agreement draft law, Lebanon Climate Act, Cartagena Dialogue meeting, Michael Haddad event, NAP consultant

## Slide 13
3. Productive sectors strengthened to promote inclusive growth and local development especially in most disadvantaged areas
Expected Results in 2018
Support to the most vulnerable host communities affected by the Syria crisis maintained and scaled up, using the process of Maps of Risks and Resources (MRR) for prioritizing the needs.
Support to the Palestinian Gatherings host communities in the areas of Shelter rehabilitation, WASH, economic development and, peace building continued.
Livelihood interventions prioritized with more focus on developing and implementing an integrated area-based economic development approach based on value chain analysis, to scale up impact and economic return.

## Slide 14
Progress and achievements in 2017
4. Lebanon has adopted measures to improve environmental Governance
Output 4.1. Low emission climate resilient actions initiated
  Indicator 4.1.1. Amount of energy saved from the implementation of decentralised and/or small-scale mitigation projects
  Baseline: 0.10 megawatts
  Target: 5.67 megawatts
  Indicator 4.1.2. No. of mitigation and adaptation awareness raising and capacity building actions taken
  Baseline: 20
  Target: 60
  Nearly 50% of the 5.67MW target has been achieved through the installation of 13 renewable energy systems in various facilities amount to 2.58MW in capacity;
  14 awareness raising and capacity building actions completed: including the issuance of technical reports such as the Derisking Renewable Energy Investments studies, PV and wind grid codes, the adoption of 2 NAMAs and the hosting of the Climate Change Cartagena Dialogue in Lebanon.
Notes: CEDRO: 3 videos, army report, wind grid code
DREG: Solar grid code, DREI, PV training
CC: 2 NAMAs, Paris agreement draft law, Lebanon Climate Act, Cartagena Dialogue meeting, Michael Haddad event, NAP consultant

## Slide 15
Progress and achievements in 2017
4. Lebanon has adopted measures to improve environmental Governance
Output 4.2. National Environmental Management Strengthened
  Indicator 4.2.1. No. of environmental initiatives implemented in productive sectors
  Baseline: 1
  Target: 25
  Indicator 4.2.2. No. of solid waste, water and waste water management initiatives implemented
  Baseline: 2
  Target: 10
  Indicator 4.2.3: volume (tons) of Ozone Depleting Substances released
  Baseline: 66.15 ODP tons
  Target: 36.78 ODP tons
  SOPs for national oil spill contingency plan prepared for LPA,
  Environmental management plans in place for 2 villages and 3 solid waste management initiatives implemented,
  Dumpsite assessment & rehabilitation of Tripoli Dumpsite finalized
  1 wastewater and 6 irrigation projects completed
  2 industries converted (foam and refrigeration) and 5.3 tons ODP tons of HCFC phased-out

## Slide 16
4. Lebanon has adopted measures to improve environmental Governance
Expected Results in 2018
Low emission climate resilient actions initiated
  Installation of renewable energy systems in industrial facilities (10 facilities)
  Integration of renewable energy systems in host-community response: hospitals and dispensaries (up to 5 sites)
  Low emission carbon development strategy
  Depollution measures installed in at least 2 industries
National Environmental Management Strengthened
  Phase out of HCFCs in 4 additional sites
  Initiation of land-use plans in 3 areas in the Qaraoun watershed
  Initiation of 1 solid waste management facility
  At least 5 irrigation/water projects (large) initiated as part of the host-communities support programme

## Slide 17
Progress on the SDG Project
Project milestones
Signed by UNDP and CDR on July 1st, 2017, in the presence of PM Hariri
Background analysis to support project deliverables
May 2017: analysis provided a brief background and progress towards the MDGs. It presented each of the 17 SDGs individually (current status and progress towards reaching each of the chosen goals and targets)
Project consists of holding a wide consultative process with partners to develop national priorities and conduct a gap analysis of the Agenda 2030.
June 2017: analysis to link the goals and clarify how achieving a goal will require tackling several others.
October 2017: comparative analysis on the VNRs of 5 selected countries against the guidelines proposed by the HLPF. This will be further complemented by experiences in other contexts to inform the outline of the report and the process leading to the elaboration of the VNR.
A situation analysis desk review will be conducted against strategic documents, existing policies, sectoral policies and laws.
Support to produce Lebanon’s 1st VNR will also be included.

## Slide 18: Key project milestones
Signature of the Project, July 2017
Assignment of National Coordinator, Sept 2017
Selection of Gap Analysis Consultant, Oct 2017
Desk review & wide consultations
Gap analysis & 1st VNR, April 2018

## Slide 19
Partners and Donors

## Slide 20
CPD Financial Update
Outcome | 2017 Target | 2018 Target
Lebanon has institutionalized mechanisms to promote peace and prevent, mitigate and manage conflict at national, municipal and community levels | 11,300,000 | 10,000,000
Government's ability to improve the performance of institutions and promote participation and accountability Increased | 10,864,000 | 12,125,000
Lebanon has adopted measures to improve environmental Governance | 15,200,000 | 11,800,000
Productive sectors strengthened to promote inclusive growth and local development especially in most disadvantaged areas | 23,000,000 | 30,000,000
Other (Privat sector + Engagement) | 1,817,585 | 650,000
Total | 62,181,585 | 64,575,000

## Slide 21
21
The New Strategic Plan answers two questions: (a) what we want UNDP to be, and (b) what we want to achieve:
By 2021, we want UNDP to:
continue as a trusted partner in a complex and evolving development landscape, strongly committed to our mandate to reduce poverty;
be more nimble, innovative and enterprising – a thought leader that succeeds in taking and managing risks;
be more effective and efficient in utilizing resources to deliver results.
By 2021, we want to catalyze tangible progress on:
eradicating poverty in all its forms – and keeping people out of poverty;
accelerating structural transformations for sustainable development, especially through innovative solutions that have multiplier effects across the SDGs;
building resilience to crises and shocks, in order to safeguard development gains.