Award 00065113 Atlas Report

| Baseline | Indicator: |
| --- | --- |
| Output 1. Abilities of the state and civil society sector institutions to effectively plan, implement, monitor and evaluate national and sub-national multi-sectoral HIV/AIDS strategies and action plans and to promote healthy life style with the focus on youth strengthened 1.1. The National HIV/AIDS programme does not ensure adequate response to the growing epidemics 1.2. A newly established state institutions have low capacity to properly plan, implement and monitor effective HIV/AIDS response in the country 1.3. Existing advocacy efforts on healthy life style among youth are insufficient to overcome HIV/AIDS, sexually transmitted infections and drug and alcohol abuse among youth Output 2. Public sector institutions strengthened in protecting the human rights of people affected by HIV/AIDS, especially youth; gender and HIV linkages addressed in policies and plans; and equal access to prevention, treatment, care and support services for men who have sex with men and transgender people provided 2.1.Low capacity of stakeholders to ensure enabling human rights environment are major barriers to effective HIV response and stigma and discrimination against people living with HIV 2.2. Gender dimension is poorly addressed in the national and regional HIV/AIDS strategies 2.3. 300 state and non-state stakeholders that developed capacities to provide prevention, treatment, care and support services to men who have sex with men and transgender people Output 4. National health care systems strengthened to ensure effective diagnostics and treatment of tuberculosis 4.1.0 state-of-the- art equipment for diagnostic of the drug-resistant tuberculosis | 1.1. The National HIV/AIDS programme with required budget and M&E plans developed, implemented and evaluated 1.2. Number of staff in state and civil society sector institutions strengthened capacities to effectively plan and implement, national and sub-national multi-sectoral HIV/AIDS strategies /action plans 1.3. Number of advocacy activities promoting healthy life style among youth implemented 2.1. Number of stakeholders (both from governmental and non-governmental organizations) that developed capacities in the area of human rights and HIV/AIDS 2.2. Number of the national and regional plans on HIV that include gender dimension of the epidemic 2.3. Number of state and non-state stakeholders that developed capacities to provide prevention, treatment, care and support services to men who have sex with men and transgender people 4.1.Number of the state-of-the- art equipment for diagnostic procured and maintained |
| 2012 Targets: | 2012 Results: |
| 1.1.The National HIV/AIDS programme for 2009-2013 with required budget and M&E plans implemented 1.2.Capacity of at least 20 staff of state and civil society sector institutions strengthened 1.3.1 healthy lifestyle promotion activity organized 2.1.50 stakeholders developed capacities in the area of human rights and HIV/AIDS 2.2.Gender mainstreamed into 3 regional plans on HIV 2.3.At least 50 additional state and non-state actors developed capacities to provide prevention, treatment, care and support services to men who have sex with men and transgender people 4.1.4 state-of-the- art equipment for diagnostic procured | 1.1.a.To determine approaches for integration of HIV/AIDS into programmatic activities of the Ministry of Economic Development and Trade, working meetings with the Ministry specialists were conducted, the terms of reference for the expert prepared, data collection for preparation of recommendations on integrating response to HIV to the MDGs and wider program of social-economic activities and development activities of the Ministry completed. 1.1.b. The methodology to accelerate MDGs was applied in the documents to assess the national program for 2009-2013, which allow to identify crucial weaknesses, bottlenecks in the Programme implementation and elaborate prioritized measures of response. Also, experts within the thematic areas "Prevention among Youth" and "Prevention among MSM" were identified and contracts were issued with consequent support in their assessment work. 1.1.c. Activities of the working group to assess the national program for 2009-2013 were supported, including preparation of individual contracts for technical coordinator and secretary of the group, assessment of the program in two thematic areas was conducted by 4 individual consultants, as well as in the areas of human rights and gender, translation material and organizational support to the group provided. 1.2.a. A nationwide meeting of chief doctors of the AIDS centers in Uzhgorod supported (17-19 September 2012). The meeting convened 57 participants from all over Ukraine and discussed new approaches for HIV and TB treatment and diagnostics, considered implications of the health care system reform and featured presentations from international partners, including presentation of UNDP on HIV and human rights issues; guide “Organization of the response to HIV/AIDS at the regional level” is being printed. Distribution of the guidance in the regions will be held in January-February 2013. 1.2.b. Activities of the working group on intellectual property rights and access to medicines supported, expert assistance and advice on how to use TRIPS flexibilities and other mechanisms to reduce the cost of medicines provided. In particular, inventory of the registered in Ukraine ART medications compiled; best international practices on using compulsory licensing analysed with informing working group; comments on the draft Cabinet resolution "On the application of CMU permission for use of intellectual property rights related to drugs" prepared for taking decisions by the re-elected working group. 1.3.a. Three regional three-days training on promoting healthy lifestyles for representatives of regional departments of the State Service of Youth and Sports (Odessa 4-6 June, Donetsk 14-16 November, Chernovtsy 4-7 December) conducted.with total participants number of 52 2.1.a. The National dialogue on HIV and Law involving more than 80 participants organized; recommendations on improvement of the national AIDS legislation and related legal acts with prioritization of the steps for inclusion in the National Action Plan were elaborated and processed with further informing and getting endorsement from the State Service on HIV/AIDS, TB and other Socially Dangerous Diseases. 2.1.b. In the framework of providing technical and expert assistance in the context of HIV legislation reform the UNDP project submitted comments on the issue of criminalization of HIV transfer and the specific suggestions on how to revise the article 130 of the Criminal Code of Ukraine. 2.1.c. In addition, the project submitted to the State Service expert comments on the draft Order set to define the most at risk populations (MARPs). Additionally, parts of the WHO’s “Guidelines on surveillance among populations most at risk for HIV” (2011) were translated into Ukrainian and submitted to the State Service for reference. 2.1.d. Two trainings on the issues of AIDS legislation, human rights and on human rights based approach were conducted for prosecutors (20 June and 23 November) and one seminar on HIV and Law issues for judges (29 November). Altogether, 126 people were trained. 2.1.e. Support provided into organizing Regional Legal Aid Network with a meeting held in Kiev on September 26-27 and development of the principles of its functioning and country level representation. Consultancy services provided to the National Human Rights Protection Movement “Gidnist” in implementation of its human rights monitoring project. 2.1.g. The information-education-communication (IEC) and promotional materials on HIV prevention, safe behavior and tolerance towards PLWHA among students 40 vocational schools in Odessa and Mykolaiv regions developed and distributed. 2.1.h.80 thematic lectures for students of vocational schools to enhance tolerance and overcoming stereotypes against HIV-positive people delivered. 2.1.i. A contest of small projects of youth NGOs to conduct innovative outreach activities for HIV prevention, safe behavior and the development of tolerance towards PLWHA in vocational schools, supported and successfully implemented 12 projects. 2.1.j. Assistance in assessing needs of the UNDP’s partners of the regional project implementation “HIV, human rights and universal access in Eastern Europe” provided. 2.1.k. In the frames of the regional project HIV, human rights and universal access in Eastern Europe a meeting of a regional legal network in HIV supported (26-27 September). 2.1.l. Participants for the e-learning on the subject of HIV and human rights (to be conducted by IDLO) identified from the non-governmental and governmental sectors; two groups of learners were formed for the September and November courses. 2.2. The project supported the development of national gender strategy on HIV and facilitated the participation of Ukraine in regional meeting on gender violence caused in Bratislava with presentation on the state of elaboration of the gender programs and perspective of their inclusion into the NAP. 2.3.a. Assessment of the system of management and provision of HIV prevention, treatment, care and support services to key populations in Odessa city conducted; assessment outcomes shared with the participants of the criteria setting training held on October 8. Process of preparation of the action plan has started. 2.3.b. Printed and disseminated among professionals and partners 1000 copies of the guidelines on men who have sex with men and HIV for various professions (journalists, doctors, police officers, judges and social workers). 2.3.c. Support to the activities of the Permanent Reference Group on MSM issues was provided, with inclusion of the project specialist into the Group in capacity of an observer and prioritization of the actions in the field of MSM and human rights. 2.3.d. In the frames of the Odessa city project expert mission and meetings with the municipal authorities were organized; research on patients rights in Ukraine Two round tables on defining criteria and approaches to the user-driven assessment of HIV services organized (October 8 and November 13). 2.3.e. A training for the AIDS centres specialists of the Donetsk region on non-discrimination and tolerance towards men who have sex with men and transgender people was conducted on 22 May. 2.3.f. Press clubs for journalists on the needs of men who have sex with men in the context of the AIDS epidemic in Lviv, Kharkiv and Donetsk were organized. 2.3. g. Significant level of activity was provided in disseminating and further promotion of the prepared (jointly by the HQ and UNDP CO) Frequently asked questions (FAQ) on the draft Law 8711 which is aimed at banning of information spread on homosexuality. The FAQ was made available to all the key players in the human rights field. There were also many letters drafted, which expressed concern over the possible adoption of the draft Law. 4.1. 4 units of the TB diagnostic equipment and 1500 pc. of the disposable materials purchased and delivered to the TB dispensaries of the cities Kramatorsk, Gorlovka, Shakhtarsk and Mariupol. |