**Fully Costed Evaluation Plan**

This evaluation plan aims to capture results, lessons learned and ensure accountability while meeting compliance requirements. With a view to align itself to the UNSDCF M&E plan, the CPD evaluation plan aims to provide information to determine programme effectiveness and decision making, while fostering continuity and mitigating against evaluation fatigue on stakeholders. The evaluations outlined in this plan are listed based on the 4 CPD outcomes and include thematic and project evaluations.

The evaluations are based on a thematic approach including governance, rule of law and security, economic empowerment. Programmes/projects that are not falling under a specific theme will be evaluated separately. Projects under vertical fund schemes such as GEF/GCF will have mid-term and terminal evaluations as per policy. The evaluations will be spread across 5 years. To inform formulation of successor programmes, existing programmes/projects that have been extended into the new CPD are expected to be evaluated in late 2021 and Q1 of 2022 using a thematic approach noting that 2021 is an election year. The successor projects will also be evaluated as themes (hence some themes will appear repeated). However, since the project titles are not yet known, the interventions falling within the themes have been listed instead. The final year (2025) has been left open to accommodate data collection for an ICPE and the evaluation of the UNSDCF to inform development of the new cooperation framework. The evaluation plan will be updated annually to accommodate new projects.

Country office evaluation capacity has been strengthened through M&E Officers taking up a certified IEO Evaluation course to effectively lead evaluations.

|  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **UNSDCF**  | **UNDP Strategic Plan Outcome** | **Evaluation Title** | **Partners joint evaluation** | **Evaluation Commissioned by** | **Type of Evaluation** | **Evaluation Completion date** | **Estimated Cost (USD)** | **Provisional Source of Funding** |
| UNSDCF Outcome 1.2 Somalis, particularly women and youth, benefit from and participate in functional, inclusive, accountable, and transparent democratic systems across all levels of government and governmental institutions. | Outcome 2: Accelerate structural transformations for sustainable development | Governance thematic evaluation (Parliamentary Support; Constitutional Review and Support; Women in Politics; REFS projects) | FGS, FMS, Local Governments, Parliament, state assemblies, relevant MDAs, electoral commission, CSO, UN Agencies, donors | UNDP  | Thematic Evaluation  | March 2022 | 90,000 | TRAC, MPTF |
| UNSDCF Outcome 1.2  | Outcome 2: Accelerate structural transformations for sustainable development | JPLG | FGS; FMS, local government | UNDP | Project evaluation | June 2023 | 20000 | MPTF |
| UNSDCF Outcome 1.2  | Outcome 2: Accelerate structural transformations for sustainable development | Governance thematic evaluation (Parliamentary Support; Constitutional Review and Support; Reconciliation) | FGS, FMS, Local Governments, Parliament, state assemblies, relevant MDAs, CSO, religious and traditional leaders; UN Agencies, donors | UNDP/RCO | Thematic evaluation  | June 2024 | 60,000 | UNDP/RCO |
| UNSDCF Outcome 1.2  | Outcome 2: Accelerate structural transformations for sustainable development | Elections project evaluation | FGS, FMS, Local Governments, Parliament, state assemblies, relevant MDAs, electoral commission, CSO, religious and traditional leaders; UN Agencies, donors | UNDP | Project evaluation | Dec 2024 | 30,000 | UNDP |
| UNSDCF Outcome 2.1 Respect, protection and promotion of human rights, gender equality, tolerance, climate security and environmental governance would be sustained by strengthened security and rule of law institutions and improved accountability mechanisms and legal frameworks. | Outcome 2: Accelerate structural transformations for sustainable development | Rule of Law & Security thematic evaluation (Security, Justice, PCVE and Police projects) | FGS, FMS, civil society, donors, private sector, UN Agencies. | UNDP | Thematic evaluation  | Oct 2021 | 60,000 | Netherlands, PBF, MPTF, UNOPS |
| UNSDCFOutcome 2.1 | Outcome 2: Accelerate structural transformations for sustainable development  | Evaluation of the Somaliland Joint Rule of Law Programme | FMS relevant MDAs, civil society, donors, academia | UNDP  | Project evaluation | Dec 2021 | 20,000 | MPTF |
| UNSDCFOutcome 2.1 | Outcome 2: Accelerate structural transformations for sustainable development | Rule of Law & Security thematic evaluation (Security, Restorative and alternative Justice, Climate security  | FGS, FMS, Local Governments, CSO, religious and traditional leaders; UN Agencies, donors | UNDP  | Thematic Evaluation | Oct 2024 | 40,000 | MPTF, TRAC |
| UNSDCFOutcome 2.1 | Outcome 2: Accelerate structural transformations for sustainable development | Tolerance and dialogue project evaluation | FGS, FMS, Local Governments, CSO, religious and traditional leaders; UN Agencies, donors | UNDP | Project evaluation | Sept 2023 | 20,000 | MPTF; Netherlands; Sweden; FCDO |
|  UNSDCFOutcome 2.1 | Outcome 2: Accelerate structural transformations for sustainable development  | Human rights project evaluation | FGS, FMS, Local Governments peace, relevant MDAs, CSO, religious and traditional leaders; UN Agencies, donors | UNDP/UNSOM | Project evaluation | Dec 2024 | 20,000 | TRAC/MPTF |
| UNSDCF Outcome 3.1 Economic governance institutions are strengthened and an enabling environment established for inclusive, sustainable and broad-based economic growth driven by the emerging small and medium sized enterprise sector | Outcome 1: Advance poverty eradication in all its forms and dimensions | Evaluation of Durable Solutions project | Relevant federal and state MDAs, private sector, civil society, UN agencies. | UNDP | Project Evaluation  | Dec 2023 | 20,000 | SDC; MPTF; PBF; TRAC |
| UNSDCF Outcome 3.1  | Outcome 1: Advance poverty eradication in all its forms and dimensions | Thematic evaluation on job creation and youth employment | Relevant federal and state MDAs, private sector, civil society, academia, IFIs, UN agencies, Somali diaspora community  | UNDP | Thematic evaluation | April 2024 | 20,000 | TRAC; MPTF |
| UNSDCF Outcome 3.1 | Outcome 3.1Advance poverty eradication in all its forms and dimensions | Evaluation of strengthening national capacities for planning, statistics and M&E project  | FGS; FMS; UN Agencies; World Bank | UNDP | Project Evaluation | June 2024 | 20,000 | TRAC; MPTF; World Bank |
| UNSDCF Outcome 3.1  | Outcome 1: Advance poverty eradication in all its forms and dimensions | Thematic evaluation on economic empowerment/ recovery  | Relevant federal and state MDAs, private sector, civil society, academia, IFIs, UN agencies  | UNDP | Thematic evaluation | Aug 2024 | 40,000 | TRAC, WB,  |
| UNSDCF Outcome 4.2 The number of people impacted by climate change, natural disasters and environmental degradation reduced. | Outcome 3 – Strengthen resilience to shocks and crises | Mid-term evaluation of the Integrated Water Resource Management project | Relevant federal and state MDAs, private sector, civil society, UN Agencies | UNDP  | Project Evaluation | May 2021 | 39,500  | GEF, TRAC  |
| UNSDCF Outcome 4.2 | Outcome 3 – Strengthen resilience to shocks and crises | Mid- term evaluation for the GCF NAP (Support for Strengthening Climate Change Adaptation Planning for the Federal Republic of Somalia) | Relevant federal and state MDAs, private sector, civil society, UN Agencies  | UNDP  | Project Evaluation | May 2021 | 20,000 | GCF, TRAC |
| UNSDCF Outcome 4.2 | Outcome 3 – Strengthen resilience to shocks and crises | Mid-term evaluation of the Cross-Cutting Capacity Development project | Relevant federal and state MDAs, private sector, civil society, UN Agencies  | UNDP  | Project Evaluation | July 2021 | 30,000  | GEF, TRAC  |
| UNSDCF Outcome 4.2 | Outcome 3 – Strengthen resilience to shocks and crises | Terminal evaluation of the Biennial Update Report (BUR) | Relevant federal and state MDAs, private sector, civil society, UN Agencies  | UNDP  | Project Evaluation | Dec 2021 | 20,000  | GEF, TRAC  |
| UNSDCF Outcome 4.2 | Outcome 3 – Strengthen resilience to shocks and crises | Terminal evaluation of the JP on Charcoal Project | Relevant federal and state MDAs, private sector, civil society, UN Agencies  | UNDP  | Project evaluation | Dec 2021 | 20,000 | MPTF |
|  UNSDCF Outcome 4.2 | Outcome 3 – Strengthen resilience to shocks and crises | Terminal evaluation of the Integrated Water Resource Management project | Relevant federal and state MDAs, private sector, civil society, UN Agencies  | UNDP  | Project Evaluation | May 2023 | 39,500  | GEF, TRAC /  |
| UNSDCF Outcome 4.2 | Outcome 3 – Strengthen resilience to shocks and crises | Terminal evaluation for the GCF NAP (Support for Strengthening Climate Change Adaptation Planning for the Federal Republic of Somalia) | Government of Somalia | UNDP  | Project Evaluation | May 2023 |  20,000  | GCF  |
| UNSDCF Outcome 4.2 | Outcome 3 – Strengthen resilience to shocks and crises | Terminal evaluation of the Cross-Cutting Capacity Development project | GEF; Government of Somalia | UNDP  | Project Evaluation | Oct 2023 | 30,000  | GEF, TRAC  |
| UNSDCF Outcome 1.2;2.1;3.1;4.2 | Outcome 1.2;2.1;3.1;4.2  | Gender thematic evaluation  | FGS; FMS; UN Agencies; Civil Society | UNDP | Thematic Evaluation | Sept 2023 | 35,000 | TRAC; MPTF; EU; World Bank |
| UNSDCFEvaluation | UNSDCF | UNSDCF evaluation | FGS; UN Agencies | RCO | UNSDCF | Q1/Q2 2025 | 50,000  | MPTF |